## General
ProjectStart | Today
2023-05-01 | 2023-05-01

## Display Settings
ShowDates | UseClassicDates | NonWorkingDayMode | HideCost | HideBilling
FALSE | FALSE | Weekends | FALSE | FALSE

## Resource Settings
DefaultUnitCost | DefaultUnitBilling | AreDisabled
1 | 1 | FALSE

## Activities
Id | DisplayOrder | Name | TargetWorkStreams | TargetResources | TargetResourceOperator | AllocatedToResources | HasNoCost | HasNoBilling | HasNoEffort | HasNoRisk | Duration | FreeSlack | TotalSlack | EarliestStartTime | LatestStartTime | EarliestFinishTime | LatestFinishTime | MinimumFreeSlack | MinimumEarliestStartTime | MinimumEarliestStartDateTime | MaximumLatestFinishTime | MaximumLatestFinishDateTime | OverrideColor | ColorFormat | Notes | Dependencies | PlanningDependencies | ResourceDependencies | Successors
1 | 0 | Start |  |  | AND |  | FALSE | FALSE | FALSE | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | FALSE | #00000000 |  |  |  |  | 2
2 | 1 | Requirements & Architecture |  | 13,15 | AND | 13,15 | FALSE | FALSE | FALSE | FALSE | 25 | 0 | 0 | 0 | 0 | 25 | 25 | [5 empty] | FALSE | #00000000 |  | 1 |  |  | 3,5
3 | 2 | Project Planning |  | 13,14,15 | AND | 13,14,15 | FALSE | FALSE | FALSE | FALSE | 15 | 0 | 0 | 25 | 25 | 40 | 40 | [5 empty] | FALSE | #00000000 |  | 2 |  | 2 | 4
4 | 3 | Management Education |  | 13,14,15 | AND | 13,14,15 | FALSE | FALSE | FALSE | FALSE | 5 | 0 | 0 | 40 | 40 | 45 | 45 | [5 empty] | FALSE | #00000000 |  | 3 |  | 3 | 5
5 | 4 | SDP Review |  | 13,14,15 | AND |  | FALSE | FALSE | FALSE | FALSE | 0 | 0 | 0 | 45 | 45 | 45 | 45 | [5 empty] | FALSE | #00000000 |  | 2,4 |  |  | 7,10
6 | 5 | UX Design |  | 2 | AND | 2 | FALSE | FALSE | FALSE | FALSE | 15 | 0 | 80 | 50 | 130 | 65 | 145 | [5 empty] | FALSE | #00000000 |  | 7 |  |  | 11
7 | 6 | Dev Training |  | 15 | AND | 15 | FALSE | FALSE | FALSE | FALSE | 5 | 0 | 0 | 45 | 45 | 50 | 50 | [5 empty] | FALSE | #00000000 |  | 5 |  | 4 | 6,8,13,14,15
8 | 7 | Test Plan | 1 | 3 | AND | 3 | FALSE | FALSE | FALSE | FALSE | 25 | 0 | 90 | 50 | 140 | 75 | 165 | [5 empty] | FALSE | #00000000 |  | 7 |  |  | 9
9 | 8 | Test Harness | 1 | 3 | AND | 3 | FALSE | FALSE | FALSE | FALSE | 25 | 90 | 90 | 75 | 165 | 100 | 190 | [5 empty] | FALSE | #00000000 |  | 8 |  | 8 | 40
10 | 9 | CM and setup | 1 | 12 | AND | 12 | FALSE | FALSE | FALSE | FALSE | 19 | 6 | 6 | 45 | 51 | 64 | 70 | [5 empty] | FALSE | #00000000 |  | 5 |  |  | 16,17,18,19,21,42
11 | 10 | UI Design |  | 2 | AND | 2 | FALSE | FALSE | FALSE | FALSE | 20 | 0 | 80 | 65 | 145 | 85 | 165 | [5 empty] | FALSE | #00000000 |  | 6 |  | 6 | 12,36,37,38
12 | 11 | Manual |  | 13 | AND | 13 | FALSE | FALSE | FALSE | FALSE | 20 | 85 | 85 | 85 | 170 | 105 | 190 | [5 empty] | FALSE | #00000000 |  | 11 |  | 4 | 41
13 | 12 | Logging | 1 |  | AND | 8 | FALSE | FALSE | FALSE | FALSE | 10 | 10 | 10 | 50 | 60 | 60 | 70 | [5 empty] | FALSE | #00000000 |  | 7 |  |  | 16,17,18,19,21,42
14 | 13 | Message Bus | 1 | 15 | AND | 15 | FALSE | FALSE | FALSE | FALSE | 15 | 5 | 5 | 50 | 55 | 65 | 70 | [5 empty] | FALSE | #00000000 |  | 7 |  | 7 | 16,17,18,19,20,21,42
15 | 14 | Security | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 20 | 0 | 0 | 50 | 50 | 70 | 70 | [5 empty] | FALSE | #00000000 |  | 7 |  |  | 16,17,18,19,21,42
16 | 15 | Metrics DB | 1 |  | AND | 7 | FALSE | FALSE | FALSE | FALSE | 5 | 15 | 15 | 70 | 85 | 75 | 90 | [5 empty] | FALSE | #00000000 |  | 10,13,14,15,42 |  |  | 22,23,43
17 | 16 | Members DB | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 5 | 0 | 0 | 75 | 75 | 80 | 80 | [5 empty] | FALSE | #00000000 |  | 10,13,14,15,21,42 |  | 21 | 18,22,24,43
18 | 17 | Portfolios DB | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 5 | 0 | 0 | 80 | 80 | 85 | 85 | [5 empty] | FALSE | #00000000 |  | 10,13,14,15,17,42 |  | 17 | 19,22,25,43
19 | 18 | Profiles DB | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 5 | 0 | 0 | 85 | 85 | 90 | 90 | [5 empty] | FALSE | #00000000 |  | 10,13,14,15,18,42 |  | 18 | 22,26,43
20 | 19 | Workflows Repository | 1 |  | AND | 8 | FALSE | FALSE | FALSE | FALSE | 15 | 5 | 5 | 70 | 75 | 85 | 90 | [5 empty] | FALSE | #00000000 |  | 14,42 |  | 13 | 27,43
21 | 20 | Regulations DB | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 5 | 0 | 0 | 70 | 70 | 75 | 75 | [5 empty] | FALSE | #00000000 |  | 10,13,14,15,42 |  | 15 | 17,22,28,43
22 | 21 | Data Migration | 1 |  | AND | 6 | FALSE | FALSE | FALSE | FALSE | 10 | 90 | 90 | 100 | 190 | 110 | 200 | [5 empty] | FALSE | #00000000 |  | 16,17,18,19,21,43 |  | 25 | 41
23 | 22 | Metrics Access | 1 |  | AND | 8 | FALSE | FALSE | FALSE | FALSE | 10 | 0 | 0 | 90 | 90 | 100 | 100 | [5 empty] | FALSE | #00000000 |  | 16,43 |  | 20 | 33,44
24 | 23 | Members Access | 1 |  | AND | 7 | FALSE | FALSE | FALSE | FALSE | 10 | 0 | 0 | 90 | 90 | 100 | 100 | [5 empty] | FALSE | #00000000 |  | 17,43 |  | 16 | 30,33,44
25 | 24 | Portfolios Access | 1 |  | AND | 6 | FALSE | FALSE | FALSE | FALSE | 10 | 0 | 10 | 90 | 100 | 100 | 110 | [5 empty] | FALSE | #00000000 |  | 18,43 |  |  | 30,31,34,44
26 | 25 | Profiles Access | 1 |  | AND | 8 | FALSE | FALSE | FALSE | FALSE | 10 | 0 | 0 | 100 | 100 | 110 | 110 | [5 empty] | FALSE | #00000000 |  | 19,43 |  | 23 | 31,44
27 | 26 | Workflows Access | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 20 | 0 | 0 | 90 | 90 | 110 | 110 | [5 empty] | FALSE | #00000000 |  | 20,43 |  | 19 | 32,44
28 | 27 | Regulations Access | 1 |  | AND | 7 | FALSE | FALSE | FALSE | FALSE | 10 | 0 | 0 | 100 | 100 | 110 | 110 | [5 empty] | FALSE | #00000000 |  | 21,43 |  | 24 | 29,44
29 | 28 | Regulations Engine | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 30 | 0 | 0 | 110 | 110 | 140 | 140 | [5 empty] | FALSE | #00000000 |  | 28,44 |  | 27 | 31,33
30 | 29 | Search Engine | 1 |  | AND | 7 | FALSE | FALSE | FALSE | FALSE | 15 | 30 | 30 | 110 | 140 | 125 | 155 | [5 empty] | FALSE | #00000000 |  | 24,25,44 |  | 28 | 34,45
31 | 30 | Analysis Engine | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 15 | 0 | 0 | 140 | 140 | 155 | 155 | [5 empty] | FALSE | #00000000 |  | 25,26,29,44 |  | 29 | 34,45
32 | 31 | Abstract Manager | 1 |  | AND | 8 | FALSE | FALSE | FALSE | FALSE | 30 | 15 | 15 | 110 | 125 | 140 | 155 | [5 empty] | FALSE | #00000000 |  | 27,44 |  | 26 | 33,34,35,45
33 | 32 | Membership Manager | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 10 | 0 | 0 | 155 | 155 | 165 | 165 | [5 empty] | FALSE | #00000000 |  | 23,24,29,32,44,45 |  | 31 | 36,37,38,46
34 | 33 | Market Manager | 1 |  | AND | 8 | FALSE | FALSE | FALSE | FALSE | 10 | 0 | 0 | 155 | 155 | 165 | 165 | [5 empty] | FALSE | #00000000 |  | 25,30,31,32,44,45 |  | 32 | 36,37,38,46
35 | 34 | Performance Manager | 1 |  | AND | 7 | FALSE | FALSE | FALSE | FALSE | 10 | 0 | 0 | 155 | 155 | 165 | 165 | [5 empty] | FALSE | #00000000 |  | 32,45 |  | 30 | 36,37,38,46
36 | 35 | Investor Portal | 1 |  | AND | 8 | FALSE | FALSE | FALSE | FALSE | 15 | 10 | 10 | 165 | 175 | 180 | 190 | [5 empty] | FALSE | #00000000 |  | 11,33,34,35,46 |  | 34 | 39,40
37 | 36 | Investee Portal | 1 |  | AND | 7 | FALSE | FALSE | FALSE | FALSE | 15 | 10 | 10 | 165 | 175 | 180 | 190 | [5 empty] | FALSE | #00000000 |  | 11,33,34,35,46 |  | 35 | 39,40
38 | 37 | Mobile App | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 25 | 0 | 0 | 165 | 165 | 190 | 190 | [5 empty] | FALSE | #00000000 |  | 11,33,34,35,46 |  | 33 | 39,40
39 | 38 | Manual Polishing | 1 | 13 | AND | 13 | FALSE | FALSE | FALSE | FALSE | 10 | 0 | 0 | 190 | 190 | 200 | 200 | [5 empty] | FALSE | #00000000 |  | 36,37,38 |  | 12 | 41
40 | 39 | System Testing | 1 | 10,11 | AND | 10,11 | FALSE | FALSE | FALSE | FALSE | 10 | 0 | 0 | 190 | 190 | 200 | 200 | [5 empty] | FALSE | #00000000 |  | 9,36,37,38 |  |  | 41
41 | 40 | System Rollout |  | 12,13,14,15 | AND | 12,13,14,15 | FALSE | FALSE | FALSE | FALSE | 10 | 0 | 0 | 200 | 200 | 210 | 210 | [5 empty] | FALSE | #00000000 |  | 12,22,39,40 |  | 4,10,14,39
42 | 41 | iFX Milestone |  |  | AND |  | FALSE | FALSE | FALSE | FALSE | 0 | 0 | 0 | 70 | 70 | 70 | 70 | [5 empty] | FALSE | #00000000 |  | 10,13,14,15 |  |  | 16,17,18,19,20,21
43 | 42 | DB Milestone |  |  | AND |  | FALSE | FALSE | FALSE | FALSE | 0 | 0 | 0 | 90 | 90 | 90 | 90 | [5 empty] | FALSE | #00000000 |  | 16,17,18,19,20,21 |  |  | 22,23,24,25,26,27,28
44 | 43 | Access Milestone |  |  | AND |  | FALSE | FALSE | FALSE | FALSE | 0 | 0 | 0 | 110 | 110 | 110 | 110 | [5 empty] | FALSE | #00000000 |  | 23,24,25,26,27,28 |  |  | 29,30,31,32,33,34
45 | 44 | Engine Milestone |  |  | AND |  | FALSE | FALSE | FALSE | FALSE | 0 | 0 | 0 | 155 | 155 | 155 | 155 | [5 empty] | FALSE | #00000000 |  | 30,31,32 |  |  | 33,34,35
46 | 45 | Manager Milestone |  |  | AND |  | FALSE | FALSE | FALSE | FALSE | 0 | 0 | 0 | 165 | 165 | 165 | 165 | [5 empty] | FALSE | #00000000 |  | 33,34,35 |  |  | 36,37,38

## Resources
Id | Name | Notes | IsExplicitTarget | IsInactive | ActivityAllocationType | InterActivityAllocationType | InterActivityPhases | UnitCost | UnitBilling | FixedCost | FixedBilling | DisplayOrder | AllocationOrder | ColorFormat
1 | DBA |  | TRUE | FALSE | Other | None |  | 700 | 700 | 0 | 0 | 14 | 0 | #0000FFFF
2 | UX |  | TRUE | FALSE | Other | None |  | 650 | 650 | 0 | 0 | 13 | 0 | #8A2BE2FF
3 | TE |  | TRUE | FALSE | Direct | Direct |  | 650 | 650 | 0 | 0 | 12 | 0 | #90EE90FF
4 | DEV6 |  | TRUE | FALSE | Direct | Direct |  | 600 | 600 | 0 | 0 | 11 | 6 | #FF0000FF
5 | DEV5 |  | TRUE | FALSE | Direct | Direct |  | 600 | 600 | 0 | 0 | 10 | 5 | #FF0000FF
6 | DEV4 |  | FALSE | FALSE | Direct | Direct |  | 600 | 600 | 0 | 0 | 9 | 4 | #FF0000FF
7 | DEV3 |  | FALSE | FALSE | Indirect | Direct |  | 600 | 600 | 0 | 0 | 8 | 3 | #FF0000FF
8 | DEV2 |  | FALSE | FALSE | Indirect | Direct |  | 700 | 700 | 0 | 0 | 7 | 2 | #FF0000FF
9 | DEV1 |  | FALSE | FALSE | Indirect | Direct |  | 750 | 750 | 0 | 0 | 6 | 1 | #FF0000FF
10 | QA2 |  | TRUE | FALSE | Indirect | Direct |  | 600 | 600 | 0 | 0 | 5 | 0 | #00CED1FF
11 | QA1 |  | TRUE | FALSE | Direct | Indirect | 1 | 600 | 600 | 0 | 0 | 4 | 0 | #00CED1FF
12 | CM |  | TRUE | FALSE | Direct | Indirect | 1 | 650 | 650 | 0 | 0 | 3 | 0 | #008B8BFF
13 | PO |  | TRUE | FALSE | Direct | Indirect |  | 1000 | 1000 | 0 | 0 | 2 | 0 | #DC143CFF
14 | PM |  | TRUE | FALSE | Direct | Indirect |  | 1000 | 1000 | 0 | 0 | 1 | 0 | #FFA500FF
15 | ARC |  | TRUE | FALSE | Direct | Indirect |  | 1000 | 1000 | 0 | 0 | 0 | 0 | #9ACD32FF

## Activity Severities
SlackLimit | CriticalityWeight | FibonacciWeight | ColorFormat
0 | 4 | 4.2361 | #000000FF
10 | 3 | 2.618 | #FF0000FF
25 | 2 | 1.618 | #FFD700FF
2147483647 | 1 | 1 | #008000FF

## Work Streams
Id | Name | IsPhase | DisplayOrder | ColorFormat
1 | Development | TRUE | 0 | #4EC114FF

## Non-Working Days
Id | Name | StartDateTime | RecurrencePattern | Notes
1 | Weekends |  | FREQ=WEEKLY;BYDAY=SA,SU
2 | Christmas Day |  | FREQ=YEARLY;BYMONTH=12;BYMONTHDAY=25

## Activity Tracker
Id | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209
1
2 | 5 | 10 | 15 | 20 | 25
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (1)
Id | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (2)
Id | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209
1 | 0
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (3)
Id | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (4)
Id | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (5)
Id | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (6)
Id | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (7)
Id | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (8)
Id | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (9)
Id | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (10)
Id | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (11)
Id | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (12)
Id | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (13)
Id | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209
1
2 | 100 | 100 | 100 | 100 | 100
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (14)
Id | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209
1
2 | 100 | 100 | 100 | 100 | 100
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (15)
Id | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209
1
2 | 90 | 100 | 100 | 100 | 100
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Chart (Activity)
Time | ARC | PM | PO | CM | QA1 | QA2 | DEV1 | DEV2 | DEV3 | DEV4 | TE | UX
0 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
5 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
6 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
8 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
9 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
10 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
11 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
12 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
13 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
14 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
15 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
16 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
17 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
18 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
19 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
20 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
21 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
22 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
23 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
24 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
25 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
26 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
27 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
28 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
29 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
30 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
31 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
32 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
33 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
34 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
35 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
36 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
37 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
38 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
39 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
40 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
41 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
42 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
43 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
44 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
45 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
46 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
47 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
48 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
49 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
50 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
51 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
52 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
53 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
54 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
55 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
56 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
57 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
58 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
59 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
60 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
61 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
62 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
63 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
64 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
65 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
66 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
67 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
68 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
69 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
70 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
71 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
72 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
73 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
74 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
75 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
76 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
77 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
78 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
79 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
80 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
81 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
82 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
83 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
84 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
85 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
86 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
87 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
88 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
89 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
90 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
91 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
92 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
93 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
94 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
95 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
96 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
97 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
98 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
99 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
100 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
101 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
102 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
103 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
104 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
105 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
106 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
107 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
108 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
109 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
110 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
111 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
112 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
113 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
114 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
115 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
116 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
117 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
118 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
119 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
120 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
121 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
122 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
123 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
124 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
125 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
126 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
127 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
128 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
129 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
130 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
131 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
132 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
133 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
134 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
135 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
136 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
137 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
138 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
139 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
140 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
141 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
142 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
143 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
144 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
145 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
146 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
147 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
148 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
149 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
150 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
151 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
152 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
153 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
154 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
155 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
156 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
157 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
158 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
159 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
160 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
161 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
162 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
163 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
164 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
165 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
166 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
167 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
168 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
169 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
170 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
171 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
172 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
173 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
174 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
175 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
176 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
177 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
178 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
179 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
180 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
181 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
182 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
183 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
184 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
185 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
186 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
187 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
188 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
189 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
190 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
191 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
192 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
193 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
194 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
195 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
196 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
197 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
198 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
199 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
200 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
201 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
202 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
203 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
204 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
205 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
206 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
207 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
208 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
209 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE

## Resource Chart (Cost)
Time | ARC | PM | PO | CM | QA1 | QA2 | DEV1 | DEV2 | DEV3 | DEV4 | TE | UX
0 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
51 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
52 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
53 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
54 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
55 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
56 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
57 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
58 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
59 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
60 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
61 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
62 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
63 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
64 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
65 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
66 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
67 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
68 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
69 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
70 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
71 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
72 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
73 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
74 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
75 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
76 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
77 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
78 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
79 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
80 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
81 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
82 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
83 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
84 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
85 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 0
86 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 0
87 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 0
88 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 0
89 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 0
90 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
91 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
92 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
93 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
94 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
95 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
96 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
97 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
98 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
99 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
100 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
101 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
102 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
103 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
104 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
105 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
106 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
107 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
108 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
109 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
110 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
111 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
112 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
113 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
114 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
115 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
116 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
117 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
118 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
119 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
120 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
121 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
122 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
123 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
124 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
125 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
126 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
127 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
128 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
129 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
130 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
131 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
132 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
133 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
134 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
135 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
136 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
137 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
138 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
139 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
140 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
141 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
142 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
143 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
144 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
145 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
146 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
147 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
148 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
149 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
150 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
151 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
152 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
153 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
154 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
155 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
156 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
157 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
158 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
159 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
160 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
161 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
162 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
163 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
164 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
165 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
166 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
167 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
168 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
169 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
170 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
171 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
172 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
173 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
174 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
175 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
176 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
177 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
178 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
179 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
180 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
181 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
182 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
183 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
184 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
185 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
186 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
187 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
188 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
189 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
190 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
191 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
192 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
193 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
194 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
195 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
196 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
197 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
198 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
199 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
200 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Resource Chart (Effort)
Time | ARC | PM | PO | CM | QA1 | QA2 | DEV1 | DEV2 | DEV3 | DEV4 | TE | UX
0 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
5 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
6 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
8 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
9 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
10 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
11 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
12 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
13 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
14 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
15 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
16 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
17 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
18 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
19 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
20 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
21 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
22 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
23 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
24 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
25 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
26 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
27 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
28 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
29 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
30 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
31 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
32 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
33 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
34 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
35 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
36 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
37 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
38 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
39 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
40 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
41 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
42 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
43 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
44 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
45 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
46 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
47 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
48 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
49 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
50 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
51 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
52 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
53 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
54 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
55 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
56 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
57 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
58 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
59 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
60 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
61 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
62 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
63 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
64 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
65 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
66 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
67 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
68 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
69 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
70 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
71 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
72 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
73 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
74 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
75 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
76 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
77 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
78 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
79 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
80 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
81 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
82 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
83 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
84 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
85 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
86 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
87 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
88 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
89 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
90 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
91 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
92 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
93 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
94 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
95 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
96 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
97 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
98 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
99 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
100 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
101 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
102 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
103 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
104 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
105 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
106 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
107 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
108 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
109 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
110 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
111 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
112 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
113 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
114 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
115 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
116 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
117 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
118 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
119 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
120 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
121 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
122 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
123 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
124 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
125 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
126 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
127 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
128 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
129 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
130 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
131 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
132 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
133 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
134 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
135 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
136 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
137 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
138 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
139 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
140 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
141 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
142 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
143 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
144 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
145 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
146 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
147 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
148 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
149 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
150 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
151 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
152 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
153 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
154 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
155 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
156 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
157 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
158 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
159 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
160 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
161 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
162 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
163 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
164 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
165 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
166 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
167 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
168 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
169 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
170 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
171 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
172 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
173 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
174 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
175 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
176 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
177 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
178 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
179 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
180 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
181 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
182 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
183 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
184 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
185 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
186 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
187 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
188 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
189 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
190 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
191 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
192 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
193 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
194 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
195 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
196 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
197 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
198 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
199 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
200 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
201 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
202 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
203 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
204 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
205 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
206 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
207 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
208 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
209 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE

## Earned-Value Chart (Plan)
Time | ActivityId | ActivityName | Value | ValuePercentage
0 | 0 |  | 0 | 0
1 | 2 | Requirements & Architecture | 2 | 0.30817
2 | 2 | Requirements & Architecture | 4 | 0.61633
3 | 2 | Requirements & Architecture | 6 | 0.9245
4 | 2 | Requirements & Architecture | 8 | 1.2327
5 | 2 | Requirements & Architecture | 10 | 1.5408
6 | 2 | Requirements & Architecture | 12 | 1.849
7 | 2 | Requirements & Architecture | 14 | 2.1572
8 | 2 | Requirements & Architecture | 16 | 2.4653
9 | 2 | Requirements & Architecture | 18 | 2.7735
10 | 2 | Requirements & Architecture | 20 | 3.0817
11 | 2 | Requirements & Architecture | 22 | 3.3898
12 | 2 | Requirements & Architecture | 24 | 3.698
13 | 2 | Requirements & Architecture | 26 | 4.0062
14 | 2 | Requirements & Architecture | 28 | 4.3143
15 | 2 | Requirements & Architecture | 30 | 4.6225
16 | 2 | Requirements & Architecture | 32 | 4.9307
17 | 2 | Requirements & Architecture | 34 | 5.2388
18 | 2 | Requirements & Architecture | 36 | 5.547
19 | 2 | Requirements & Architecture | 38 | 5.8552
20 | 2 | Requirements & Architecture | 40 | 6.1633
21 | 2 | Requirements & Architecture | 42 | 6.4715
22 | 2 | Requirements & Architecture | 44 | 6.7797
23 | 2 | Requirements & Architecture | 46 | 7.0878
24 | 2 | Requirements & Architecture | 48 | 7.396
25 | 2 | Requirements & Architecture | 50 | 7.7042
26 | 3 | Project Planning | 53 | 8.1664
27 | 3 | Project Planning | 56 | 8.6287
28 | 3 | Project Planning | 59 | 9.0909
29 | 3 | Project Planning | 62 | 9.5532
30 | 3 | Project Planning | 65 | 10.0154
31 | 3 | Project Planning | 68 | 10.4777
32 | 3 | Project Planning | 71 | 10.9399
33 | 3 | Project Planning | 74 | 11.4022
34 | 3 | Project Planning | 77 | 11.8644
35 | 3 | Project Planning | 80 | 12.3267
36 | 3 | Project Planning | 83 | 12.7889
37 | 3 | Project Planning | 86 | 13.2512
38 | 3 | Project Planning | 89 | 13.7134
39 | 3 | Project Planning | 92 | 14.1757
40 | 3 | Project Planning | 95 | 14.6379
41 | 4 | Management Education | 98 | 15.1002
42 | 4 | Management Education | 101 | 15.5624
43 | 4 | Management Education | 104 | 16.0247
44 | 4 | Management Education | 107 | 16.4869
45 | 4 | Management Education | 110 | 16.9492
46 | 7 | Dev Training | 112 | 17.2573
46 | 10 | CM and setup | 112 | 17.2573
47 | 7 | Dev Training | 114 | 17.5655
47 | 10 | CM and setup | 114 | 17.5655
48 | 7 | Dev Training | 116 | 17.8737
48 | 10 | CM and setup | 116 | 17.8737
49 | 7 | Dev Training | 118 | 18.1818
49 | 10 | CM and setup | 118 | 18.1818
50 | 7 | Dev Training | 120 | 18.49
50 | 10 | CM and setup | 120 | 18.49
51 | 13 | Logging | 126 | 19.4145
51 | 10 | CM and setup | 126 | 19.4145
51 | 6 | UX Design | 126 | 19.4145
51 | 14 | Message Bus | 126 | 19.4145
51 | 15 | Security | 126 | 19.4145
51 | 8 | Test Plan | 126 | 19.4145
52 | 13 | Logging | 132 | 20.339
52 | 10 | CM and setup | 132 | 20.339
52 | 6 | UX Design | 132 | 20.339
52 | 14 | Message Bus | 132 | 20.339
52 | 15 | Security | 132 | 20.339
52 | 8 | Test Plan | 132 | 20.339
53 | 13 | Logging | 138 | 21.2635
53 | 10 | CM and setup | 138 | 21.2635
53 | 6 | UX Design | 138 | 21.2635
53 | 14 | Message Bus | 138 | 21.2635
53 | 15 | Security | 138 | 21.2635
53 | 8 | Test Plan | 138 | 21.2635
54 | 13 | Logging | 144 | 22.188
54 | 10 | CM and setup | 144 | 22.188
54 | 6 | UX Design | 144 | 22.188
54 | 14 | Message Bus | 144 | 22.188
54 | 15 | Security | 144 | 22.188
54 | 8 | Test Plan | 144 | 22.188
55 | 13 | Logging | 150 | 23.1125
55 | 10 | CM and setup | 150 | 23.1125
55 | 6 | UX Design | 150 | 23.1125
55 | 14 | Message Bus | 150 | 23.1125
55 | 15 | Security | 150 | 23.1125
55 | 8 | Test Plan | 150 | 23.1125
56 | 13 | Logging | 156 | 24.037
56 | 10 | CM and setup | 156 | 24.037
56 | 6 | UX Design | 156 | 24.037
56 | 14 | Message Bus | 156 | 24.037
56 | 15 | Security | 156 | 24.037
56 | 8 | Test Plan | 156 | 24.037
57 | 13 | Logging | 162 | 24.9615
57 | 10 | CM and setup | 162 | 24.9615
57 | 6 | UX Design | 162 | 24.9615
57 | 14 | Message Bus | 162 | 24.9615
57 | 15 | Security | 162 | 24.9615
57 | 8 | Test Plan | 162 | 24.9615
58 | 13 | Logging | 168 | 25.886
58 | 10 | CM and setup | 168 | 25.886
58 | 6 | UX Design | 168 | 25.886
58 | 14 | Message Bus | 168 | 25.886
58 | 15 | Security | 168 | 25.886
58 | 8 | Test Plan | 168 | 25.886
59 | 13 | Logging | 174 | 26.8105
59 | 10 | CM and setup | 174 | 26.8105
59 | 6 | UX Design | 174 | 26.8105
59 | 14 | Message Bus | 174 | 26.8105
59 | 15 | Security | 174 | 26.8105
59 | 8 | Test Plan | 174 | 26.8105
60 | 13 | Logging | 180 | 27.735
60 | 10 | CM and setup | 180 | 27.735
60 | 6 | UX Design | 180 | 27.735
60 | 14 | Message Bus | 180 | 27.735
60 | 15 | Security | 180 | 27.735
60 | 8 | Test Plan | 180 | 27.735
61 | 10 | CM and setup | 185 | 28.5054
61 | 6 | UX Design | 185 | 28.5054
61 | 14 | Message Bus | 185 | 28.5054
61 | 15 | Security | 185 | 28.5054
61 | 8 | Test Plan | 185 | 28.5054
62 | 10 | CM and setup | 190 | 29.2758
62 | 6 | UX Design | 190 | 29.2758
62 | 14 | Message Bus | 190 | 29.2758
62 | 15 | Security | 190 | 29.2758
62 | 8 | Test Plan | 190 | 29.2758
63 | 10 | CM and setup | 195 | 30.0462
63 | 6 | UX Design | 195 | 30.0462
63 | 14 | Message Bus | 195 | 30.0462
63 | 15 | Security | 195 | 30.0462
63 | 8 | Test Plan | 195 | 30.0462
64 | 10 | CM and setup | 200 | 30.8166
64 | 6 | UX Design | 200 | 30.8166
64 | 14 | Message Bus | 200 | 30.8166
64 | 15 | Security | 200 | 30.8166
64 | 8 | Test Plan | 200 | 30.8166
65 | 6 | UX Design | 204 | 31.433
65 | 14 | Message Bus | 204 | 31.433
65 | 15 | Security | 204 | 31.433
65 | 8 | Test Plan | 204 | 31.433
66 | 15 | Security | 207 | 31.8952
66 | 8 | Test Plan | 207 | 31.8952
66 | 11 | UI Design | 207 | 31.8952
67 | 15 | Security | 210 | 32.3575
67 | 8 | Test Plan | 210 | 32.3575
67 | 11 | UI Design | 210 | 32.3575
68 | 15 | Security | 213 | 32.8197
68 | 8 | Test Plan | 213 | 32.8197
68 | 11 | UI Design | 213 | 32.8197
69 | 15 | Security | 216 | 33.282
69 | 8 | Test Plan | 216 | 33.282
69 | 11 | UI Design | 216 | 33.282
70 | 15 | Security | 219 | 33.7442
70 | 8 | Test Plan | 219 | 33.7442
70 | 11 | UI Design | 219 | 33.7442
71 | 8 | Test Plan | 224 | 34.5146
71 | 16 | Metrics DB | 224 | 34.5146
71 | 21 | Regulations DB | 224 | 34.5146
71 | 11 | UI Design | 224 | 34.5146
71 | 20 | Workflows Repository | 224 | 34.5146
72 | 8 | Test Plan | 229 | 35.2851
72 | 16 | Metrics DB | 229 | 35.2851
72 | 21 | Regulations DB | 229 | 35.2851
72 | 11 | UI Design | 229 | 35.2851
72 | 20 | Workflows Repository | 229 | 35.2851
73 | 8 | Test Plan | 234 | 36.0555
73 | 16 | Metrics DB | 234 | 36.0555
73 | 21 | Regulations DB | 234 | 36.0555
73 | 11 | UI Design | 234 | 36.0555
73 | 20 | Workflows Repository | 234 | 36.0555
74 | 8 | Test Plan | 239 | 36.8259
74 | 16 | Metrics DB | 239 | 36.8259
74 | 21 | Regulations DB | 239 | 36.8259
74 | 11 | UI Design | 239 | 36.8259
74 | 20 | Workflows Repository | 239 | 36.8259
75 | 8 | Test Plan | 244 | 37.5963
75 | 16 | Metrics DB | 244 | 37.5963
75 | 21 | Regulations DB | 244 | 37.5963
75 | 11 | UI Design | 244 | 37.5963
75 | 20 | Workflows Repository | 244 | 37.5963
76 | 17 | Members DB | 248 | 38.2126
76 | 11 | UI Design | 248 | 38.2126
76 | 20 | Workflows Repository | 248 | 38.2126
76 | 9 | Test Harness | 248 | 38.2126
77 | 17 | Members DB | 252 | 38.829
77 | 11 | UI Design | 252 | 38.829
77 | 20 | Workflows Repository | 252 | 38.829
77 | 9 | Test Harness | 252 | 38.829
78 | 17 | Members DB | 256 | 39.4453
78 | 11 | UI Design | 256 | 39.4453
78 | 20 | Workflows Repository | 256 | 39.4453
78 | 9 | Test Harness | 256 | 39.4453
79 | 17 | Members DB | 260 | 40.0616
79 | 11 | UI Design | 260 | 40.0616
79 | 20 | Workflows Repository | 260 | 40.0616
79 | 9 | Test Harness | 260 | 40.0616
80 | 17 | Members DB | 264 | 40.678
80 | 11 | UI Design | 264 | 40.678
80 | 20 | Workflows Repository | 264 | 40.678
80 | 9 | Test Harness | 264 | 40.678
81 | 11 | UI Design | 268 | 41.2943
81 | 20 | Workflows Repository | 268 | 41.2943
81 | 18 | Portfolios DB | 268 | 41.2943
81 | 9 | Test Harness | 268 | 41.2943
82 | 11 | UI Design | 272 | 41.9106
82 | 20 | Workflows Repository | 272 | 41.9106
82 | 18 | Portfolios DB | 272 | 41.9106
82 | 9 | Test Harness | 272 | 41.9106
83 | 11 | UI Design | 276 | 42.527
83 | 20 | Workflows Repository | 276 | 42.527
83 | 18 | Portfolios DB | 276 | 42.527
83 | 9 | Test Harness | 276 | 42.527
84 | 11 | UI Design | 280 | 43.1433
84 | 20 | Workflows Repository | 280 | 43.1433
84 | 18 | Portfolios DB | 280 | 43.1433
84 | 9 | Test Harness | 280 | 43.1433
85 | 11 | UI Design | 284 | 43.7596
85 | 20 | Workflows Repository | 284 | 43.7596
85 | 18 | Portfolios DB | 284 | 43.7596
85 | 9 | Test Harness | 284 | 43.7596
86 | 19 | Profiles DB | 287 | 44.2219
86 | 9 | Test Harness | 287 | 44.2219
86 | 12 | Manual | 287 | 44.2219
87 | 19 | Profiles DB | 290 | 44.6841
87 | 9 | Test Harness | 290 | 44.6841
87 | 12 | Manual | 290 | 44.6841
88 | 19 | Profiles DB | 293 | 45.1464
88 | 9 | Test Harness | 293 | 45.1464
88 | 12 | Manual | 293 | 45.1464
89 | 19 | Profiles DB | 296 | 45.6086
89 | 9 | Test Harness | 296 | 45.6086
89 | 12 | Manual | 296 | 45.6086
90 | 19 | Profiles DB | 299 | 46.0709
90 | 9 | Test Harness | 299 | 46.0709
90 | 12 | Manual | 299 | 46.0709
91 | 9 | Test Harness | 305 | 46.9954
91 | 23 | Metrics Access | 305 | 46.9954
91 | 24 | Members Access | 305 | 46.9954
91 | 25 | Portfolios Access | 305 | 46.9954
91 | 12 | Manual | 305 | 46.9954
91 | 27 | Workflows Access | 305 | 46.9954
92 | 9 | Test Harness | 311 | 47.9199
92 | 23 | Metrics Access | 311 | 47.9199
92 | 24 | Members Access | 311 | 47.9199
92 | 25 | Portfolios Access | 311 | 47.9199
92 | 12 | Manual | 311 | 47.9199
92 | 27 | Workflows Access | 311 | 47.9199
93 | 9 | Test Harness | 317 | 48.8444
93 | 23 | Metrics Access | 317 | 48.8444
93 | 24 | Members Access | 317 | 48.8444
93 | 25 | Portfolios Access | 317 | 48.8444
93 | 12 | Manual | 317 | 48.8444
93 | 27 | Workflows Access | 317 | 48.8444
94 | 9 | Test Harness | 323 | 49.7689
94 | 23 | Metrics Access | 323 | 49.7689
94 | 24 | Members Access | 323 | 49.7689
94 | 25 | Portfolios Access | 323 | 49.7689
94 | 12 | Manual | 323 | 49.7689
94 | 27 | Workflows Access | 323 | 49.7689
95 | 9 | Test Harness | 329 | 50.6934
95 | 23 | Metrics Access | 329 | 50.6934
95 | 24 | Members Access | 329 | 50.6934
95 | 25 | Portfolios Access | 329 | 50.6934
95 | 12 | Manual | 329 | 50.6934
95 | 27 | Workflows Access | 329 | 50.6934
96 | 9 | Test Harness | 335 | 51.6179
96 | 23 | Metrics Access | 335 | 51.6179
96 | 24 | Members Access | 335 | 51.6179
96 | 25 | Portfolios Access | 335 | 51.6179
96 | 12 | Manual | 335 | 51.6179
96 | 27 | Workflows Access | 335 | 51.6179
97 | 9 | Test Harness | 341 | 52.5424
97 | 23 | Metrics Access | 341 | 52.5424
97 | 24 | Members Access | 341 | 52.5424
97 | 25 | Portfolios Access | 341 | 52.5424
97 | 12 | Manual | 341 | 52.5424
97 | 27 | Workflows Access | 341 | 52.5424
98 | 9 | Test Harness | 347 | 53.4669
98 | 23 | Metrics Access | 347 | 53.4669
98 | 24 | Members Access | 347 | 53.4669
98 | 25 | Portfolios Access | 347 | 53.4669
98 | 12 | Manual | 347 | 53.4669
98 | 27 | Workflows Access | 347 | 53.4669
99 | 9 | Test Harness | 353 | 54.3914
99 | 23 | Metrics Access | 353 | 54.3914
99 | 24 | Members Access | 353 | 54.3914
99 | 25 | Portfolios Access | 353 | 54.3914
99 | 12 | Manual | 353 | 54.3914
99 | 27 | Workflows Access | 353 | 54.3914
100 | 9 | Test Harness | 359 | 55.3159
100 | 23 | Metrics Access | 359 | 55.3159
100 | 24 | Members Access | 359 | 55.3159
100 | 25 | Portfolios Access | 359 | 55.3159
100 | 12 | Manual | 359 | 55.3159
100 | 27 | Workflows Access | 359 | 55.3159
101 | 12 | Manual | 364 | 56.0863
101 | 27 | Workflows Access | 364 | 56.0863
101 | 22 | Data Migration | 364 | 56.0863
101 | 26 | Profiles Access | 364 | 56.0863
101 | 28 | Regulations Access | 364 | 56.0863
102 | 12 | Manual | 369 | 56.8567
102 | 27 | Workflows Access | 369 | 56.8567
102 | 22 | Data Migration | 369 | 56.8567
102 | 26 | Profiles Access | 369 | 56.8567
102 | 28 | Regulations Access | 369 | 56.8567
103 | 12 | Manual | 374 | 57.6271
103 | 27 | Workflows Access | 374 | 57.6271
103 | 22 | Data Migration | 374 | 57.6271
103 | 26 | Profiles Access | 374 | 57.6271
103 | 28 | Regulations Access | 374 | 57.6271
104 | 12 | Manual | 379 | 58.3975
104 | 27 | Workflows Access | 379 | 58.3975
104 | 22 | Data Migration | 379 | 58.3975
104 | 26 | Profiles Access | 379 | 58.3975
104 | 28 | Regulations Access | 379 | 58.3975
105 | 12 | Manual | 384 | 59.168
105 | 27 | Workflows Access | 384 | 59.168
105 | 22 | Data Migration | 384 | 59.168
105 | 26 | Profiles Access | 384 | 59.168
105 | 28 | Regulations Access | 384 | 59.168
106 | 27 | Workflows Access | 388 | 59.7843
106 | 22 | Data Migration | 388 | 59.7843
106 | 26 | Profiles Access | 388 | 59.7843
106 | 28 | Regulations Access | 388 | 59.7843
107 | 27 | Workflows Access | 392 | 60.4006
107 | 22 | Data Migration | 392 | 60.4006
107 | 26 | Profiles Access | 392 | 60.4006
107 | 28 | Regulations Access | 392 | 60.4006
108 | 27 | Workflows Access | 396 | 61.0169
108 | 22 | Data Migration | 396 | 61.0169
108 | 26 | Profiles Access | 396 | 61.0169
108 | 28 | Regulations Access | 396 | 61.0169
109 | 27 | Workflows Access | 400 | 61.6333
109 | 22 | Data Migration | 400 | 61.6333
109 | 26 | Profiles Access | 400 | 61.6333
109 | 28 | Regulations Access | 400 | 61.6333
110 | 27 | Workflows Access | 404 | 62.2496
110 | 22 | Data Migration | 404 | 62.2496
110 | 26 | Profiles Access | 404 | 62.2496
110 | 28 | Regulations Access | 404 | 62.2496
111 | 30 | Search Engine | 407 | 62.7119
111 | 29 | Regulations Engine | 407 | 62.7119
111 | 32 | Abstract Manager | 407 | 62.7119
112 | 30 | Search Engine | 410 | 63.1741
112 | 29 | Regulations Engine | 410 | 63.1741
112 | 32 | Abstract Manager | 410 | 63.1741
113 | 30 | Search Engine | 413 | 63.6364
113 | 29 | Regulations Engine | 413 | 63.6364
113 | 32 | Abstract Manager | 413 | 63.6364
114 | 30 | Search Engine | 416 | 64.0986
114 | 29 | Regulations Engine | 416 | 64.0986
114 | 32 | Abstract Manager | 416 | 64.0986
115 | 30 | Search Engine | 419 | 64.5609
115 | 29 | Regulations Engine | 419 | 64.5609
115 | 32 | Abstract Manager | 419 | 64.5609
116 | 30 | Search Engine | 422 | 65.0231
116 | 29 | Regulations Engine | 422 | 65.0231
116 | 32 | Abstract Manager | 422 | 65.0231
117 | 30 | Search Engine | 425 | 65.4854
117 | 29 | Regulations Engine | 425 | 65.4854
117 | 32 | Abstract Manager | 425 | 65.4854
118 | 30 | Search Engine | 428 | 65.9476
118 | 29 | Regulations Engine | 428 | 65.9476
118 | 32 | Abstract Manager | 428 | 65.9476
119 | 30 | Search Engine | 431 | 66.4099
119 | 29 | Regulations Engine | 431 | 66.4099
119 | 32 | Abstract Manager | 431 | 66.4099
120 | 30 | Search Engine | 434 | 66.8721
120 | 29 | Regulations Engine | 434 | 66.8721
120 | 32 | Abstract Manager | 434 | 66.8721
121 | 30 | Search Engine | 437 | 67.3344
121 | 29 | Regulations Engine | 437 | 67.3344
121 | 32 | Abstract Manager | 437 | 67.3344
122 | 30 | Search Engine | 440 | 67.7966
122 | 29 | Regulations Engine | 440 | 67.7966
122 | 32 | Abstract Manager | 440 | 67.7966
123 | 30 | Search Engine | 443 | 68.2589
123 | 29 | Regulations Engine | 443 | 68.2589
123 | 32 | Abstract Manager | 443 | 68.2589
124 | 30 | Search Engine | 446 | 68.7211
124 | 29 | Regulations Engine | 446 | 68.7211
124 | 32 | Abstract Manager | 446 | 68.7211
125 | 30 | Search Engine | 449 | 69.1834
125 | 29 | Regulations Engine | 449 | 69.1834
125 | 32 | Abstract Manager | 449 | 69.1834
126 | 29 | Regulations Engine | 451 | 69.4915
126 | 32 | Abstract Manager | 451 | 69.4915
127 | 29 | Regulations Engine | 453 | 69.7997
127 | 32 | Abstract Manager | 453 | 69.7997
128 | 29 | Regulations Engine | 455 | 70.1079
128 | 32 | Abstract Manager | 455 | 70.1079
129 | 29 | Regulations Engine | 457 | 70.416
129 | 32 | Abstract Manager | 457 | 70.416
130 | 29 | Regulations Engine | 459 | 70.7242
130 | 32 | Abstract Manager | 459 | 70.7242
131 | 29 | Regulations Engine | 461 | 71.0324
131 | 32 | Abstract Manager | 461 | 71.0324
132 | 29 | Regulations Engine | 463 | 71.3405
132 | 32 | Abstract Manager | 463 | 71.3405
133 | 29 | Regulations Engine | 465 | 71.6487
133 | 32 | Abstract Manager | 465 | 71.6487
134 | 29 | Regulations Engine | 467 | 71.9569
134 | 32 | Abstract Manager | 467 | 71.9569
135 | 29 | Regulations Engine | 469 | 72.265
135 | 32 | Abstract Manager | 469 | 72.265
136 | 29 | Regulations Engine | 471 | 72.5732
136 | 32 | Abstract Manager | 471 | 72.5732
137 | 29 | Regulations Engine | 473 | 72.8814
137 | 32 | Abstract Manager | 473 | 72.8814
138 | 29 | Regulations Engine | 475 | 73.1895
138 | 32 | Abstract Manager | 475 | 73.1895
139 | 29 | Regulations Engine | 477 | 73.4977
139 | 32 | Abstract Manager | 477 | 73.4977
140 | 29 | Regulations Engine | 479 | 73.8059
140 | 32 | Abstract Manager | 479 | 73.8059
141 | 31 | Analysis Engine | 480 | 73.9599
142 | 31 | Analysis Engine | 481 | 74.114
143 | 31 | Analysis Engine | 482 | 74.2681
144 | 31 | Analysis Engine | 483 | 74.4222
145 | 31 | Analysis Engine | 484 | 74.5763
146 | 31 | Analysis Engine | 485 | 74.7304
147 | 31 | Analysis Engine | 486 | 74.8844
148 | 31 | Analysis Engine | 487 | 75.0385
149 | 31 | Analysis Engine | 488 | 75.1926
150 | 31 | Analysis Engine | 489 | 75.3467
151 | 31 | Analysis Engine | 490 | 75.5008
152 | 31 | Analysis Engine | 491 | 75.6549
153 | 31 | Analysis Engine | 492 | 75.8089
154 | 31 | Analysis Engine | 493 | 75.963
155 | 31 | Analysis Engine | 494 | 76.1171
156 | 33 | Membership Manager | 497 | 76.5794
156 | 34 | Market Manager | 497 | 76.5794
156 | 35 | Performance Manager | 497 | 76.5794
157 | 33 | Membership Manager | 500 | 77.0416
157 | 34 | Market Manager | 500 | 77.0416
157 | 35 | Performance Manager | 500 | 77.0416
158 | 33 | Membership Manager | 503 | 77.5039
158 | 34 | Market Manager | 503 | 77.5039
158 | 35 | Performance Manager | 503 | 77.5039
159 | 33 | Membership Manager | 506 | 77.9661
159 | 34 | Market Manager | 506 | 77.9661
159 | 35 | Performance Manager | 506 | 77.9661
160 | 33 | Membership Manager | 509 | 78.4284
160 | 34 | Market Manager | 509 | 78.4284
160 | 35 | Performance Manager | 509 | 78.4284
161 | 33 | Membership Manager | 512 | 78.8906
161 | 34 | Market Manager | 512 | 78.8906
161 | 35 | Performance Manager | 512 | 78.8906
162 | 33 | Membership Manager | 515 | 79.3529
162 | 34 | Market Manager | 515 | 79.3529
162 | 35 | Performance Manager | 515 | 79.3529
163 | 33 | Membership Manager | 518 | 79.8151
163 | 34 | Market Manager | 518 | 79.8151
163 | 35 | Performance Manager | 518 | 79.8151
164 | 33 | Membership Manager | 521 | 80.2773
164 | 34 | Market Manager | 521 | 80.2773
164 | 35 | Performance Manager | 521 | 80.2773
165 | 33 | Membership Manager | 524 | 80.7396
165 | 34 | Market Manager | 524 | 80.7396
165 | 35 | Performance Manager | 524 | 80.7396
166 | 36 | Investor Portal | 527 | 81.2018
166 | 37 | Investee Portal | 527 | 81.2018
166 | 38 | Mobile App | 527 | 81.2018
167 | 36 | Investor Portal | 530 | 81.6641
167 | 37 | Investee Portal | 530 | 81.6641
167 | 38 | Mobile App | 530 | 81.6641
168 | 36 | Investor Portal | 533 | 82.1263
168 | 37 | Investee Portal | 533 | 82.1263
168 | 38 | Mobile App | 533 | 82.1263
169 | 36 | Investor Portal | 536 | 82.5886
169 | 37 | Investee Portal | 536 | 82.5886
169 | 38 | Mobile App | 536 | 82.5886
170 | 36 | Investor Portal | 539 | 83.0508
170 | 37 | Investee Portal | 539 | 83.0508
170 | 38 | Mobile App | 539 | 83.0508
171 | 36 | Investor Portal | 542 | 83.5131
171 | 37 | Investee Portal | 542 | 83.5131
171 | 38 | Mobile App | 542 | 83.5131
172 | 36 | Investor Portal | 545 | 83.9753
172 | 37 | Investee Portal | 545 | 83.9753
172 | 38 | Mobile App | 545 | 83.9753
173 | 36 | Investor Portal | 548 | 84.4376
173 | 37 | Investee Portal | 548 | 84.4376
173 | 38 | Mobile App | 548 | 84.4376
174 | 36 | Investor Portal | 551 | 84.8998
174 | 37 | Investee Portal | 551 | 84.8998
174 | 38 | Mobile App | 551 | 84.8998
175 | 36 | Investor Portal | 554 | 85.3621
175 | 37 | Investee Portal | 554 | 85.3621
175 | 38 | Mobile App | 554 | 85.3621
176 | 36 | Investor Portal | 557 | 85.8243
176 | 37 | Investee Portal | 557 | 85.8243
176 | 38 | Mobile App | 557 | 85.8243
177 | 36 | Investor Portal | 560 | 86.2866
177 | 37 | Investee Portal | 560 | 86.2866
177 | 38 | Mobile App | 560 | 86.2866
178 | 36 | Investor Portal | 563 | 86.7488
178 | 37 | Investee Portal | 563 | 86.7488
178 | 38 | Mobile App | 563 | 86.7488
179 | 36 | Investor Portal | 566 | 87.2111
179 | 37 | Investee Portal | 566 | 87.2111
179 | 38 | Mobile App | 566 | 87.2111
180 | 36 | Investor Portal | 569 | 87.6733
180 | 37 | Investee Portal | 569 | 87.6733
180 | 38 | Mobile App | 569 | 87.6733
181 | 38 | Mobile App | 570 | 87.8274
182 | 38 | Mobile App | 571 | 87.9815
183 | 38 | Mobile App | 572 | 88.1356
184 | 38 | Mobile App | 573 | 88.2897
185 | 38 | Mobile App | 574 | 88.4438
186 | 38 | Mobile App | 575 | 88.5978
187 | 38 | Mobile App | 576 | 88.7519
188 | 38 | Mobile App | 577 | 88.906
189 | 38 | Mobile App | 578 | 89.0601
190 | 38 | Mobile App | 579 | 89.2142
191 | 39 | Manual Polishing | 582 | 89.6764
191 | 40 | System Testing | 582 | 89.6764
192 | 39 | Manual Polishing | 585 | 90.1387
192 | 40 | System Testing | 585 | 90.1387
193 | 39 | Manual Polishing | 588 | 90.6009
193 | 40 | System Testing | 588 | 90.6009
194 | 39 | Manual Polishing | 591 | 91.0632
194 | 40 | System Testing | 591 | 91.0632
195 | 39 | Manual Polishing | 594 | 91.5254
195 | 40 | System Testing | 594 | 91.5254
196 | 39 | Manual Polishing | 597 | 91.9877
196 | 40 | System Testing | 597 | 91.9877
197 | 39 | Manual Polishing | 600 | 92.4499
197 | 40 | System Testing | 600 | 92.4499
198 | 39 | Manual Polishing | 603 | 92.9122
198 | 40 | System Testing | 603 | 92.9122
199 | 39 | Manual Polishing | 606 | 93.3744
199 | 40 | System Testing | 606 | 93.3744
200 | 39 | Manual Polishing | 609 | 93.8367
200 | 40 | System Testing | 609 | 93.8367
201 | 41 | System Rollout | 613 | 94.453
202 | 41 | System Rollout | 617 | 95.0693
203 | 41 | System Rollout | 621 | 95.6857
204 | 41 | System Rollout | 625 | 96.302
205 | 41 | System Rollout | 629 | 96.9183
206 | 41 | System Rollout | 633 | 97.5347
207 | 41 | System Rollout | 637 | 98.151
208 | 41 | System Rollout | 641 | 98.7673
209 | 41 | System Rollout | 645 | 99.3837
210 | 41 | System Rollout | 649 | 100

## Earned-Value Chart (Effort)
Time | ActivityId | ActivityName | Value | ValuePercentage
0 | 0 |  | 0 | 0
1 | 1 |  | 2.9 | 0.44684
1 | 2 |  | 2.9 | 0.44684
1 | 2 |  | 2.9 | 0.44684
1 | 2 |  | 2.9 | 0.44684
2 | 2 |  | 5.9 | 0.90909
2 | 2 |  | 5.9 | 0.90909
2 | 2 |  | 5.9 | 0.90909
3 | 2 |  | 8.9 | 1.3713
3 | 2 |  | 8.9 | 1.3713
3 | 2 |  | 8.9 | 1.3713
4 | 2 |  | 11.9 | 1.8336
4 | 2 |  | 11.9 | 1.8336
4 | 2 |  | 11.9 | 1.8336
5 | 2 |  | 14.9 | 2.2958
5 | 2 |  | 14.9 | 2.2958
5 | 2 |  | 14.9 | 2.2958

## Earned-Value Chart (Progress)
Time | ActivityId | ActivityName | Value | ValuePercentage
0 | 0 |  | 0 | 0
1 | 2 | Requirements & Architecture | 2.5 | 0.38521
2 | 2 | Requirements & Architecture | 5 | 0.77042
3 | 2 | Requirements & Architecture | 7.5 | 1.1556
4 | 2 | Requirements & Architecture | 10 | 1.5408
5 | 2 | Requirements & Architecture | 12.5 | 1.926