## General
ProjectStart | Today
2026-01-05 | 2026-01-19

## Display Settings
ShowDates | UseClassicDates | NonWorkingDayMode | HideCost | HideBilling
FALSE | FALSE | Weekends | FALSE | FALSE

## Resource Settings
DefaultUnitCost | DefaultUnitBilling | AreDisabled
1 | 1 | FALSE

## Activities
Id | DisplayOrder | Name | TargetWorkStreams | TargetResources | TargetResourceOperator | AllocatedToResources | HasNoCost | HasNoBilling | HasNoEffort | HasNoRisk | Duration | MostLikelyDuration | OptimisticDuration | PessimisticDuration | ExpectedDuration | StandardDeviation | FreeSlack | TotalSlack | EarliestStartTime | LatestStartTime | EarliestFinishTime | LatestFinishTime | MinimumFreeSlack | MinimumEarliestStartTime | MinimumEarliestStartDateTime | MaximumLatestFinishTime | MaximumLatestFinishDateTime | OverrideColor | ColorFormat | Notes | Dependencies | PlanningDependencies | ResourceDependencies | Successors
1 | 0 | Start |  |  | AND |  | FALSE | FALSE | FALSE | FALSE | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | [5 empty] | FALSE | #00000000 |  |  |  |  | 2
2 | 1 | Requirements & Architecture |  | 13,15 | AND | 13,15 | FALSE | FALSE | FALSE | FALSE | 25 | 25 |  |  | 25 | 0 | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-30 | 2026-01-30 | [5 empty] | FALSE | #00000000 |  | 1 |  |  | 3,5
3 | 2 | Project Planning |  | 13,14,15 | AND | 13,14,15 | FALSE | FALSE | FALSE | FALSE | 15 | 15 |  |  | 15 | 0 | 0 | 0 | 2026-01-30 | 2026-01-30 | 2026-02-14 | 2026-02-14 | [5 empty] | FALSE | #00000000 |  | 2 |  | 2 | 4
4 | 3 | Management Education |  | 13,14,15 | AND | 13,14,15 | FALSE | FALSE | FALSE | FALSE | 5 | 5 |  |  | 5 | 0 | 0 | 0 | 2026-02-14 | 2026-02-14 | 2026-02-19 | 2026-02-19 | [5 empty] | FALSE | #00000000 |  | 3 |  | 3 | 5
5 | 4 | SDP Review |  | 13,14,15 | AND |  | FALSE | FALSE | FALSE | FALSE | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | [5 empty] | FALSE | #00000000 |  | 2,4 |  |  | 7,10
6 | 5 | UX Design |  | 2 | AND | 2 | FALSE | FALSE | FALSE | FALSE | 15 | 15 |  |  | 15 | 0 | 0 | 80 | 2026-02-24 | 2026-05-15 | 2026-03-11 | 2026-05-30 | [5 empty] | FALSE | #00000000 |  | 7 |  |  | 11
7 | 6 | Dev Training |  | 15 | AND | 15 | FALSE | FALSE | FALSE | FALSE | 5 | 5 |  |  | 5 | 0 | 0 | 0 | 2026-02-19 | 2026-02-19 | 2026-02-24 | 2026-02-24 | [5 empty] | FALSE | #00000000 |  | 5 |  | 4 | 6,8,13,14,15
8 | 7 | Test Plan | 1 | 3 | AND | 3 | FALSE | FALSE | FALSE | FALSE | 25 | 25 |  |  | 25 | 0 | 0 | 90 | 2026-02-24 | 2026-05-25 | 2026-03-21 | 2026-06-19 | [5 empty] | FALSE | #00000000 |  | 7 |  |  | 9
9 | 8 | Test Harness | 1 | 3 | AND | 3 | FALSE | FALSE | FALSE | FALSE | 25 | 25 |  |  | 25 | 0 | 90 | 90 | 2026-03-21 | 2026-06-19 | 2026-04-15 | 2026-07-14 | [5 empty] | FALSE | #00000000 |  | 8 |  | 8 | 40
10 | 9 | CM and setup | 1 | 12 | AND | 12 | FALSE | FALSE | FALSE | FALSE | 19 | 19 |  |  | 19 | 0 | 6 | 6 | 2026-02-19 | 2026-02-25 | 2026-03-10 | 2026-03-16 | [5 empty] | FALSE | #00000000 |  | 5 |  |  | 16,17,18,19,21,42
11 | 10 | UI Design |  | 2 | AND | 2 | FALSE | FALSE | FALSE | FALSE | 20 | 20 |  |  | 20 | 0 | 0 | 80 | 2026-03-11 | 2026-05-30 | 2026-03-31 | 2026-06-19 | [5 empty] | FALSE | #00000000 |  | 6 |  | 6 | 12,36,37,38
12 | 11 | Manual |  | 13 | AND | 13 | FALSE | FALSE | FALSE | FALSE | 20 | 20 |  |  | 20 | 0 | 85 | 85 | 2026-03-31 | 2026-06-24 | 2026-04-20 | 2026-07-14 | [5 empty] | FALSE | #00000000 |  | 11 |  | 4 | 41
13 | 12 | Logging | 1 |  | AND | 8 | FALSE | FALSE | FALSE | FALSE | 10 | 10 |  |  | 10 | 0 | 10 | 10 | 2026-02-24 | 2026-03-06 | 2026-03-06 | 2026-03-16 | [5 empty] | FALSE | #00000000 |  | 7 |  |  | 16,17,18,19,21,42
14 | 13 | Message Bus | 1 | 15 | AND | 15 | FALSE | FALSE | FALSE | FALSE | 15 | 15 |  |  | 15 | 0 | 5 | 5 | 2026-02-24 | 2026-03-01 | 2026-03-11 | 2026-03-16 | [5 empty] | FALSE | #00000000 |  | 7 |  | 7 | 16,17,18,19,20,21,42
15 | 14 | Security | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 20 | 20 |  |  | 20 | 0 | 0 | 0 | 2026-02-24 | 2026-02-24 | 2026-03-16 | 2026-03-16 | [5 empty] | FALSE | #00000000 |  | 7 |  |  | 16,17,18,19,21,42
16 | 15 | Metrics DB | 1 |  | AND | 7 | FALSE | FALSE | FALSE | FALSE | 5 | 5 |  |  | 5 | 0 | 15 | 15 | 2026-03-16 | 2026-03-31 | 2026-03-21 | 2026-04-05 | [5 empty] | FALSE | #00000000 |  | 10,13,14,15,42 |  |  | 22,23,43
17 | 16 | Members DB | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 5 | 5 |  |  | 5 | 0 | 0 | 0 | 2026-03-21 | 2026-03-21 | 2026-03-26 | 2026-03-26 | [5 empty] | FALSE | #00000000 |  | 10,13,14,15,21,42 |  | 21 | 18,22,24,43
18 | 17 | Portfolios DB | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 5 | 5 |  |  | 5 | 0 | 0 | 0 | 2026-03-26 | 2026-03-26 | 2026-03-31 | 2026-03-31 | [5 empty] | FALSE | #00000000 |  | 10,13,14,15,17,42 |  | 17 | 19,22,25,43
19 | 18 | Profiles DB | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 5 | 5 |  |  | 5 | 0 | 0 | 0 | 2026-03-31 | 2026-03-31 | 2026-04-05 | 2026-04-05 | [5 empty] | FALSE | #00000000 |  | 10,13,14,15,18,42 |  | 18 | 22,26,43
20 | 19 | Workflows Repository | 1 |  | AND | 8 | FALSE | FALSE | FALSE | FALSE | 15 | 15 |  |  | 15 | 0 | 5 | 5 | 2026-03-16 | 2026-03-21 | 2026-03-31 | 2026-04-05 | [5 empty] | FALSE | #00000000 |  | 14,42 |  | 13 | 27,43
21 | 20 | Regulations DB | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 5 | 5 |  |  | 5 | 0 | 0 | 0 | 2026-03-16 | 2026-03-16 | 2026-03-21 | 2026-03-21 | [5 empty] | FALSE | #00000000 |  | 10,13,14,15,42 |  | 15 | 17,22,28,43
22 | 21 | Data Migration | 1 |  | AND | 6 | FALSE | FALSE | FALSE | FALSE | 10 | 10 |  |  | 10 | 0 | 90 | 90 | 2026-04-15 | 2026-07-14 | 2026-04-25 | 2026-07-24 | [5 empty] | FALSE | #00000000 |  | 16,17,18,19,21,43 |  | 25 | 41
23 | 22 | Metrics Access | 1 |  | AND | 8 | FALSE | FALSE | FALSE | FALSE | 10 | 10 |  |  | 10 | 0 | 0 | 0 | 2026-04-05 | 2026-04-05 | 2026-04-15 | 2026-04-15 | [5 empty] | FALSE | #00000000 |  | 16,43 |  | 20 | 33,44
24 | 23 | Members Access | 1 |  | AND | 7 | FALSE | FALSE | FALSE | FALSE | 10 | 10 |  |  | 10 | 0 | 0 | 0 | 2026-04-05 | 2026-04-05 | 2026-04-15 | 2026-04-15 | [5 empty] | FALSE | #00000000 |  | 17,43 |  | 16 | 30,33,44
25 | 24 | Portfolios Access | 1 |  | AND | 6 | FALSE | FALSE | FALSE | FALSE | 10 | 10 |  |  | 10 | 0 | 0 | 10 | 2026-04-05 | 2026-04-15 | 2026-04-15 | 2026-04-25 | [5 empty] | FALSE | #00000000 |  | 18,43 |  |  | 30,31,34,44
26 | 25 | Profiles Access | 1 |  | AND | 8 | FALSE | FALSE | FALSE | FALSE | 10 | 10 |  |  | 10 | 0 | 0 | 0 | 2026-04-15 | 2026-04-15 | 2026-04-25 | 2026-04-25 | [5 empty] | FALSE | #00000000 |  | 19,43 |  | 23 | 31,44
27 | 26 | Workflows Access | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 20 | 20 |  |  | 20 | 0 | 0 | 0 | 2026-04-05 | 2026-04-05 | 2026-04-25 | 2026-04-25 | [5 empty] | FALSE | #00000000 |  | 20,43 |  | 19 | 32,44
28 | 27 | Regulations Access | 1 |  | AND | 7 | FALSE | FALSE | FALSE | FALSE | 10 | 10 |  |  | 10 | 0 | 0 | 0 | 2026-04-15 | 2026-04-15 | 2026-04-25 | 2026-04-25 | [5 empty] | FALSE | #00000000 |  | 21,43 |  | 24 | 29,44
29 | 28 | Regulations Engine | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 30 | 30 |  |  | 30 | 0 | 0 | 0 | 2026-04-25 | 2026-04-25 | 2026-05-25 | 2026-05-25 | [5 empty] | FALSE | #00000000 |  | 28,44 |  | 27 | 31,33
30 | 29 | Search Engine | 1 |  | AND | 7 | FALSE | FALSE | FALSE | FALSE | 15 | 15 |  |  | 15 | 0 | 30 | 30 | 2026-04-25 | 2026-05-25 | 2026-05-10 | 2026-06-09 | [5 empty] | FALSE | #00000000 |  | 24,25,44 |  | 28 | 34,45
31 | 30 | Analysis Engine | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 15 | 15 |  |  | 15 | 0 | 0 | 0 | 2026-05-25 | 2026-05-25 | 2026-06-09 | 2026-06-09 | [5 empty] | FALSE | #00000000 |  | 25,26,29,44 |  | 29 | 34,45
32 | 31 | Abstract Manager | 1 |  | AND | 8 | FALSE | FALSE | FALSE | FALSE | 30 | 30 |  |  | 30 | 0 | 15 | 15 | 2026-04-25 | 2026-05-10 | 2026-05-25 | 2026-06-09 | [5 empty] | FALSE | #00000000 |  | 27,44 |  | 26 | 33,34,35,45
33 | 32 | Membership Manager | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 10 | 10 |  |  | 10 | 0 | 0 | 0 | 2026-06-09 | 2026-06-09 | 2026-06-19 | 2026-06-19 | [5 empty] | FALSE | #00000000 |  | 23,24,29,32,44,45 |  | 31 | 36,37,38,46
34 | 33 | Market Manager | 1 |  | AND | 8 | FALSE | FALSE | FALSE | FALSE | 10 | 10 |  |  | 10 | 0 | 0 | 0 | 2026-06-09 | 2026-06-09 | 2026-06-19 | 2026-06-19 | [5 empty] | FALSE | #00000000 |  | 25,30,31,32,44,45 |  | 32 | 36,37,38,46
35 | 34 | Performance Manager | 1 |  | AND | 7 | FALSE | FALSE | FALSE | FALSE | 10 | 10 |  |  | 10 | 0 | 0 | 0 | 2026-06-09 | 2026-06-09 | 2026-06-19 | 2026-06-19 | [5 empty] | FALSE | #00000000 |  | 32,45 |  | 30 | 36,37,38,46
36 | 35 | Investor Portal | 1 |  | AND | 8 | FALSE | FALSE | FALSE | FALSE | 15 | 15 |  |  | 15 | 0 | 10 | 10 | 2026-06-19 | 2026-06-29 | 2026-07-04 | 2026-07-14 | [5 empty] | FALSE | #00000000 |  | 11,33,34,35,46 |  | 34 | 39,40
37 | 36 | Investee Portal | 1 |  | AND | 7 | FALSE | FALSE | FALSE | FALSE | 15 | 15 |  |  | 15 | 0 | 10 | 10 | 2026-06-19 | 2026-06-29 | 2026-07-04 | 2026-07-14 | [5 empty] | FALSE | #00000000 |  | 11,33,34,35,46 |  | 35 | 39,40
38 | 37 | Mobile App | 1 |  | AND | 9 | FALSE | FALSE | FALSE | FALSE | 25 | 25 |  |  | 25 | 0 | 0 | 0 | 2026-06-19 | 2026-06-19 | 2026-07-14 | 2026-07-14 | [5 empty] | FALSE | #00000000 |  | 11,33,34,35,46 |  | 33 | 39,40
39 | 38 | Manual Polishing | 1 | 13 | AND | 13 | FALSE | FALSE | FALSE | FALSE | 10 | 10 |  |  | 10 | 0 | 0 | 0 | 2026-07-14 | 2026-07-14 | 2026-07-24 | 2026-07-24 | [5 empty] | FALSE | #00000000 |  | 36,37,38 |  | 12 | 41
40 | 39 | System Testing | 1 | 10,11 | AND | 10,11 | FALSE | FALSE | FALSE | FALSE | 10 | 10 |  |  | 10 | 0 | 0 | 0 | 2026-07-14 | 2026-07-14 | 2026-07-24 | 2026-07-24 | [5 empty] | FALSE | #00000000 |  | 9,36,37,38 |  |  | 41
41 | 40 | System Rollout |  | 12,13,14,15 | AND | 12,13,14,15 | FALSE | FALSE | FALSE | FALSE | 10 | 10 |  |  | 10 | 0 | 0 | 0 | 2026-07-24 | 2026-07-24 | 2026-08-03 | 2026-08-03 | [5 empty] | FALSE | #00000000 |  | 12,22,39,40 |  | 4,10,14,39
42 | 41 | iFX Milestone |  |  | AND |  | FALSE | FALSE | FALSE | FALSE | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | [5 empty] | FALSE | #00000000 |  | 10,13,14,15 |  |  | 16,17,18,19,20,21
43 | 42 | DB Milestone |  |  | AND |  | FALSE | FALSE | FALSE | FALSE | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 2026-04-05 | 2026-04-05 | 2026-04-05 | 2026-04-05 | [5 empty] | FALSE | #00000000 |  | 16,17,18,19,20,21 |  |  | 22,23,24,25,26,27,28
44 | 43 | Access Milestone |  |  | AND |  | FALSE | FALSE | FALSE | FALSE | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-04-25 | [5 empty] | FALSE | #00000000 |  | 23,24,25,26,27,28 |  |  | 29,30,31,32,33,34
45 | 44 | Engine Milestone |  |  | AND |  | FALSE | FALSE | FALSE | FALSE | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-09 | [5 empty] | FALSE | #00000000 |  | 30,31,32 |  |  | 33,34,35
46 | 45 | Manager Milestone |  |  | AND |  | FALSE | FALSE | FALSE | FALSE | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-19 | [5 empty] | FALSE | #00000000 |  | 33,34,35 |  |  | 36,37,38

## Resources
Id | Name | Notes | IsExplicitTarget | IsInactive | ActivityAllocationType | InterActivityAllocationType | InterActivityPhases | UnitCost | UnitBilling | FixedCost | FixedBilling | DisplayOrder | AllocationOrder | ColorFormat
1 | DBA |  | TRUE | FALSE | Other | None |  | 700 | 700 | 0 | 0 | 14 | 0 | #0000FFFF
2 | UX |  | TRUE | FALSE | Other | None |  | 650 | 650 | 0 | 0 | 13 | 0 | #8A2BE2FF
3 | TE |  | TRUE | FALSE | Direct | Direct |  | 650 | 650 | 0 | 0 | 12 | 0 | #90EE90FF
4 | DEV6 |  | TRUE | FALSE | Direct | Direct |  | 600 | 600 | 0 | 0 | 11 | 6 | #FF0000FF
5 | DEV5 |  | TRUE | FALSE | Direct | Direct |  | 600 | 600 | 0 | 0 | 10 | 5 | #FF0000FF
6 | DEV4 |  | FALSE | FALSE | Direct | Direct |  | 600 | 600 | 0 | 0 | 9 | 4 | #FF0000FF
7 | DEV3 |  | FALSE | FALSE | Indirect | Direct |  | 600 | 600 | 0 | 0 | 8 | 3 | #FF0000FF
8 | DEV2 |  | FALSE | FALSE | Indirect | Direct |  | 700 | 700 | 0 | 0 | 7 | 2 | #FF0000FF
9 | DEV1 |  | FALSE | FALSE | Indirect | Direct |  | 750 | 750 | 0 | 0 | 6 | 1 | #FF0000FF
10 | QA2 |  | TRUE | FALSE | Indirect | Direct |  | 600 | 600 | 0 | 0 | 5 | 0 | #00CED1FF
11 | QA1 |  | TRUE | FALSE | Direct | Indirect | 1 | 600 | 600 | 0 | 0 | 4 | 0 | #00CED1FF
12 | CM |  | TRUE | FALSE | Direct | Indirect | 1 | 650 | 650 | 0 | 0 | 3 | 0 | #008B8BFF
13 | PO |  | TRUE | FALSE | Direct | Indirect |  | 1000 | 1000 | 0 | 0 | 2 | 0 | #DC143CFF
14 | PM |  | TRUE | FALSE | Direct | Indirect |  | 1000 | 1000 | 0 | 0 | 1 | 0 | #FFA500FF
15 | ARC |  | TRUE | FALSE | Direct | Indirect |  | 1000 | 1000 | 0 | 0 | 0 | 0 | #9ACD32FF

## Activity Severities
SlackLimit | CriticalityWeight | FibonacciWeight | ColorFormat
0 | 4 | 4.2361 | #000000FF
10 | 3 | 2.618 | #FF0000FF
25 | 2 | 1.618 | #FFD700FF
2147483647 | 1 | 1 | #008000FF

## Work Streams
Id | Name | IsPhase | DisplayOrder | ColorFormat
1 | Development | TRUE | 0 | #4EC114FF

## Non-Working Days
Id | Name | StartDateTime | RecurrencePattern | Notes
1 | Weekends |  | FREQ=WEEKLY;BYDAY=SA,SU
2 | Christmas Day |  | FREQ=YEARLY;BYMONTH=12;BYMONTHDAY=25

## Activity Tracker
Id | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
1
2 | 5 | 10 | 15 | 20 | 25
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (1)
Id | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (2)
Id | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
1 | 0
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (3)
Id | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (4)
Id | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (5)
Id | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (6)
Id | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (7)
Id | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (8)
Id | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (9)
Id | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (10)
Id | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (11)
Id | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (12)
Id | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (13)
Id | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
1
2 | 100 | 100 | 100 | 100 | 100
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (14)
Id | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
1
2 | 100 | 100 | 100 | 100 | 100
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Tracker (15)
Id | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
1
2 | 90 | 100 | 100 | 100 | 100
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Resource Chart (Activity)
Time | ARC | PM | PO | CM | QA1 | QA2 | DEV1 | DEV2 | DEV3 | DEV4 | TE | UX
2026-01-05 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-06 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-07 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-08 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-09 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-10 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-11 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-12 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-13 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-14 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-15 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-16 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-17 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-18 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-19 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-20 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-21 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-22 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-23 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-24 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-25 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-26 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-27 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-28 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-29 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-30 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-31 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-01 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-02 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-03 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-04 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-05 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-06 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-07 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-08 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-09 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-10 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-11 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-12 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-13 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-14 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-15 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-16 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-17 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-18 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-19 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-20 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-21 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-22 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-23 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-24 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-02-25 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-02-26 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-02-27 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-02-28 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-01 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-02 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-03 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-04 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-05 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-06 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-07 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-08 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-09 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-10 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-11 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-12 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-13 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-14 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-15 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-16 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-17 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-18 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-19 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-20 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-21 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-22 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-23 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-24 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-25 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-26 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-27 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-28 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-29 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-30 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-31 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
2026-04-01 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
2026-04-02 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
2026-04-03 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
2026-04-04 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
2026-04-05 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-06 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-07 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-08 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-09 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-10 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-11 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-12 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-13 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-14 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-15 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-16 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-17 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-18 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-19 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-20 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-21 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-22 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-23 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-24 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-25 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-04-26 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-04-27 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-04-28 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-04-29 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-04-30 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-01 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-02 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-03 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-04 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-05 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-06 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-07 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-08 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-09 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-10 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-11 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-12 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-13 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-14 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-15 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-16 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-17 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-18 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-19 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-20 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-21 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-22 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-23 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-24 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-25 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-26 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-27 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-28 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-29 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-30 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-31 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-01 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-02 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-03 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-04 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-05 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-06 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-07 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-08 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-09 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-10 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-11 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-12 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-13 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-14 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-15 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-16 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-17 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-18 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-19 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-20 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-21 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-22 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-23 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-24 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-25 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-26 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-27 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-28 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-29 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-30 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-07-01 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-07-02 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-07-03 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-07-04 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-05 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-06 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-07 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-08 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-09 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-10 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-11 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-12 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-13 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-14 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-16 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-17 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-19 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-20 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-21 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-22 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-23 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-24 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-25 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-26 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-27 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-28 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-29 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-30 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-31 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-08-01 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-08-02 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE

## Resource Chart (Cost)
Time | ARC | PM | PO | CM | QA1 | QA2 | DEV1 | DEV2 | DEV3 | DEV4 | TE | UX
2026-01-05 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-06 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-07 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-08 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-09 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-10 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-11 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-12 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-13 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-14 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-15 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-16 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-17 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-18 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-19 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-20 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-21 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-22 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-23 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-24 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-25 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-26 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-27 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-28 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-29 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-30 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-31 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-01 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-02 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-03 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-04 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-05 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-06 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-07 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-08 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-09 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-10 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-11 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-12 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-13 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-14 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-15 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-16 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-17 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-18 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-19 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-20 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-21 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-22 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-23 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-24 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-02-25 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-02-26 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-02-27 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-02-28 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-03-01 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-03-02 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-03-03 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-03-04 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-03-05 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-03-06 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-03-07 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-03-08 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-03-09 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-03-10 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-03-11 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-03-12 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-03-13 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-03-14 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-03-15 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 0 | 0 | 650 | 650
2026-03-16 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
2026-03-17 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
2026-03-18 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
2026-03-19 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
2026-03-20 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
2026-03-21 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
2026-03-22 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
2026-03-23 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
2026-03-24 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
2026-03-25 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
2026-03-26 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
2026-03-27 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
2026-03-28 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
2026-03-29 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
2026-03-30 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 650
2026-03-31 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 0
2026-04-01 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 0
2026-04-02 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 0
2026-04-03 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 0
2026-04-04 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 650 | 0
2026-04-05 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
2026-04-06 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
2026-04-07 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
2026-04-08 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
2026-04-09 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
2026-04-10 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
2026-04-11 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
2026-04-12 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
2026-04-13 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
2026-04-14 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 650 | 0
2026-04-15 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
2026-04-16 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
2026-04-17 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
2026-04-18 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
2026-04-19 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
2026-04-20 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
2026-04-21 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
2026-04-22 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
2026-04-23 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
2026-04-24 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 600 | 0 | 0
2026-04-25 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-04-26 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-04-27 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-04-28 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-04-29 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-04-30 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-01 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-02 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-03 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-04 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-05 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-06 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-07 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-08 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-09 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-10 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-11 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-12 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-13 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-14 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-15 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-16 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-17 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-18 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-19 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-20 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-21 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-22 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-23 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-24 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-25 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-26 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-27 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-28 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-29 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-30 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-05-31 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-01 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-02 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-03 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-04 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-05 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-06 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-07 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-08 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-09 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-10 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-11 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-12 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-13 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-14 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-15 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-16 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-17 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-18 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-19 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-20 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-21 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-22 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-23 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-24 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-25 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-26 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-27 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-28 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-29 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-06-30 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-07-01 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-07-02 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-07-03 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 700 | 600 | 0 | 0 | 0
2026-07-04 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
2026-07-05 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
2026-07-06 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
2026-07-07 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
2026-07-08 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
2026-07-09 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
2026-07-10 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
2026-07-11 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
2026-07-12 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
2026-07-13 | 1000 | 1000 | 1000 | 650 | 600 | 0 | 750 | 0 | 0 | 0 | 0 | 0
2026-07-14 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-15 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-16 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-17 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-18 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-19 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-20 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-21 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-22 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-23 | 1000 | 1000 | 1000 | 650 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-24 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-25 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-26 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-27 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-28 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-29 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-30 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-31 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-01 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-02 | 1000 | 1000 | 1000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Resource Chart (Effort)
Time | ARC | PM | PO | CM | QA1 | QA2 | DEV1 | DEV2 | DEV3 | DEV4 | TE | UX
2026-01-05 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-06 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-07 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-08 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-09 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-10 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-11 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-12 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-13 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-14 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-15 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-16 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-17 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-18 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-19 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-20 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-21 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-22 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-23 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-24 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-25 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-26 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-27 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-28 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-29 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-30 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-01-31 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-01 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-02 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-03 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-04 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-05 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-06 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-07 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-08 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-09 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-10 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-11 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-12 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-13 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-14 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-15 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-16 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-17 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-18 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-19 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-20 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-21 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-22 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-23 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-02-24 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-02-25 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-02-26 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-02-27 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-02-28 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-01 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-02 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-03 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-04 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-05 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-06 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-07 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-08 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-09 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-10 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-11 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-12 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-13 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-14 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-15 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
2026-03-16 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-17 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-18 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-19 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-20 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-21 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-22 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-23 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-24 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-25 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-26 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-27 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-28 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-29 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-30 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE
2026-03-31 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
2026-04-01 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
2026-04-02 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
2026-04-03 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
2026-04-04 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE
2026-04-05 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-06 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-07 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-08 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-09 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-10 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-11 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-12 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-13 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-14 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2026-04-15 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-16 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-17 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-18 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-19 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-20 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-21 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-22 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-23 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-24 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
2026-04-25 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-04-26 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-04-27 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-04-28 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-04-29 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-04-30 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-01 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-02 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-03 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-04 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-05 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-06 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-07 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-08 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-09 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-10 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-11 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-12 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-13 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-14 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-15 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-16 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-17 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-18 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-19 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-20 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-21 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-22 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-23 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-24 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-25 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-26 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-27 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-28 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-29 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-30 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-05-31 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-01 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-02 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-03 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-04 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-05 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-06 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-07 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-08 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-09 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-10 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-11 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-12 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-13 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-14 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-15 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-16 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-17 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-18 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-19 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-20 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-21 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-22 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-23 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-24 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-25 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-26 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-27 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-28 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-29 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-06-30 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-07-01 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-07-02 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-07-03 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
2026-07-04 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-05 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-06 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-07 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-08 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-09 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-10 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-11 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-12 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-13 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-14 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-16 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-17 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-18 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-19 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-20 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-21 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-22 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-23 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-24 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-25 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-26 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-27 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-28 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-29 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-30 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-07-31 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-08-01 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2026-08-02 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE

## Earned-Value Chart (Plan)
Time | ActivityId | ActivityName | Value | ValuePercentage
2026-01-05 | 0 |  | 0 | 0
2026-01-06 | 2 | Requirements & Architecture | 2 | 0.30817
2026-01-07 | 2 | Requirements & Architecture | 4 | 0.61633
2026-01-08 | 2 | Requirements & Architecture | 6 | 0.9245
2026-01-09 | 2 | Requirements & Architecture | 8 | 1.2327
2026-01-10 | 2 | Requirements & Architecture | 10 | 1.5408
2026-01-11 | 2 | Requirements & Architecture | 12 | 1.849
2026-01-12 | 2 | Requirements & Architecture | 14 | 2.1572
2026-01-13 | 2 | Requirements & Architecture | 16 | 2.4653
2026-01-14 | 2 | Requirements & Architecture | 18 | 2.7735
2026-01-15 | 2 | Requirements & Architecture | 20 | 3.0817
2026-01-16 | 2 | Requirements & Architecture | 22 | 3.3898
2026-01-17 | 2 | Requirements & Architecture | 24 | 3.698
2026-01-18 | 2 | Requirements & Architecture | 26 | 4.0062
2026-01-19 | 2 | Requirements & Architecture | 28 | 4.3143
2026-01-20 | 2 | Requirements & Architecture | 30 | 4.6225
2026-01-21 | 2 | Requirements & Architecture | 32 | 4.9307
2026-01-22 | 2 | Requirements & Architecture | 34 | 5.2388
2026-01-23 | 2 | Requirements & Architecture | 36 | 5.547
2026-01-24 | 2 | Requirements & Architecture | 38 | 5.8552
2026-01-25 | 2 | Requirements & Architecture | 40 | 6.1633
2026-01-26 | 2 | Requirements & Architecture | 42 | 6.4715
2026-01-27 | 2 | Requirements & Architecture | 44 | 6.7797
2026-01-28 | 2 | Requirements & Architecture | 46 | 7.0878
2026-01-29 | 2 | Requirements & Architecture | 48 | 7.396
2026-01-30 | 2 | Requirements & Architecture | 50 | 7.7042
2026-01-31 | 3 | Project Planning | 53 | 8.1664
2026-02-01 | 3 | Project Planning | 56 | 8.6287
2026-02-02 | 3 | Project Planning | 59 | 9.0909
2026-02-03 | 3 | Project Planning | 62 | 9.5532
2026-02-04 | 3 | Project Planning | 65 | 10.0154
2026-02-05 | 3 | Project Planning | 68 | 10.4777
2026-02-06 | 3 | Project Planning | 71 | 10.9399
2026-02-07 | 3 | Project Planning | 74 | 11.4022
2026-02-08 | 3 | Project Planning | 77 | 11.8644
2026-02-09 | 3 | Project Planning | 80 | 12.3267
2026-02-10 | 3 | Project Planning | 83 | 12.7889
2026-02-11 | 3 | Project Planning | 86 | 13.2512
2026-02-12 | 3 | Project Planning | 89 | 13.7134
2026-02-13 | 3 | Project Planning | 92 | 14.1757
2026-02-14 | 3 | Project Planning | 95 | 14.6379
2026-02-15 | 4 | Management Education | 98 | 15.1002
2026-02-16 | 4 | Management Education | 101 | 15.5624
2026-02-17 | 4 | Management Education | 104 | 16.0247
2026-02-18 | 4 | Management Education | 107 | 16.4869
2026-02-19 | 4 | Management Education | 110 | 16.9492
2026-02-20 | 7 | Dev Training | 112 | 17.2573
2026-02-20 | 10 | CM and setup | 112 | 17.2573
2026-02-21 | 7 | Dev Training | 114 | 17.5655
2026-02-21 | 10 | CM and setup | 114 | 17.5655
2026-02-22 | 7 | Dev Training | 116 | 17.8737
2026-02-22 | 10 | CM and setup | 116 | 17.8737
2026-02-23 | 7 | Dev Training | 118 | 18.1818
2026-02-23 | 10 | CM and setup | 118 | 18.1818
2026-02-24 | 7 | Dev Training | 120 | 18.49
2026-02-24 | 10 | CM and setup | 120 | 18.49
2026-02-25 | 13 | Logging | 126 | 19.4145
2026-02-25 | 10 | CM and setup | 126 | 19.4145
2026-02-25 | 6 | UX Design | 126 | 19.4145
2026-02-25 | 14 | Message Bus | 126 | 19.4145
2026-02-25 | 15 | Security | 126 | 19.4145
2026-02-25 | 8 | Test Plan | 126 | 19.4145
2026-02-26 | 13 | Logging | 132 | 20.339
2026-02-26 | 10 | CM and setup | 132 | 20.339
2026-02-26 | 6 | UX Design | 132 | 20.339
2026-02-26 | 14 | Message Bus | 132 | 20.339
2026-02-26 | 15 | Security | 132 | 20.339
2026-02-26 | 8 | Test Plan | 132 | 20.339
2026-02-27 | 13 | Logging | 138 | 21.2635
2026-02-27 | 10 | CM and setup | 138 | 21.2635
2026-02-27 | 6 | UX Design | 138 | 21.2635
2026-02-27 | 14 | Message Bus | 138 | 21.2635
2026-02-27 | 15 | Security | 138 | 21.2635
2026-02-27 | 8 | Test Plan | 138 | 21.2635
2026-02-28 | 13 | Logging | 144 | 22.188
2026-02-28 | 10 | CM and setup | 144 | 22.188
2026-02-28 | 6 | UX Design | 144 | 22.188
2026-02-28 | 14 | Message Bus | 144 | 22.188
2026-02-28 | 15 | Security | 144 | 22.188
2026-02-28 | 8 | Test Plan | 144 | 22.188
2026-03-01 | 13 | Logging | 150 | 23.1125
2026-03-01 | 10 | CM and setup | 150 | 23.1125
2026-03-01 | 6 | UX Design | 150 | 23.1125
2026-03-01 | 14 | Message Bus | 150 | 23.1125
2026-03-01 | 15 | Security | 150 | 23.1125
2026-03-01 | 8 | Test Plan | 150 | 23.1125
2026-03-02 | 13 | Logging | 156 | 24.037
2026-03-02 | 10 | CM and setup | 156 | 24.037
2026-03-02 | 6 | UX Design | 156 | 24.037
2026-03-02 | 14 | Message Bus | 156 | 24.037
2026-03-02 | 15 | Security | 156 | 24.037
2026-03-02 | 8 | Test Plan | 156 | 24.037
2026-03-03 | 13 | Logging | 162 | 24.9615
2026-03-03 | 10 | CM and setup | 162 | 24.9615
2026-03-03 | 6 | UX Design | 162 | 24.9615
2026-03-03 | 14 | Message Bus | 162 | 24.9615
2026-03-03 | 15 | Security | 162 | 24.9615
2026-03-03 | 8 | Test Plan | 162 | 24.9615
2026-03-04 | 13 | Logging | 168 | 25.886
2026-03-04 | 10 | CM and setup | 168 | 25.886
2026-03-04 | 6 | UX Design | 168 | 25.886
2026-03-04 | 14 | Message Bus | 168 | 25.886
2026-03-04 | 15 | Security | 168 | 25.886
2026-03-04 | 8 | Test Plan | 168 | 25.886
2026-03-05 | 13 | Logging | 174 | 26.8105
2026-03-05 | 10 | CM and setup | 174 | 26.8105
2026-03-05 | 6 | UX Design | 174 | 26.8105
2026-03-05 | 14 | Message Bus | 174 | 26.8105
2026-03-05 | 15 | Security | 174 | 26.8105
2026-03-05 | 8 | Test Plan | 174 | 26.8105
2026-03-06 | 13 | Logging | 180 | 27.735
2026-03-06 | 10 | CM and setup | 180 | 27.735
2026-03-06 | 6 | UX Design | 180 | 27.735
2026-03-06 | 14 | Message Bus | 180 | 27.735
2026-03-06 | 15 | Security | 180 | 27.735
2026-03-06 | 8 | Test Plan | 180 | 27.735
2026-03-07 | 10 | CM and setup | 185 | 28.5054
2026-03-07 | 6 | UX Design | 185 | 28.5054
2026-03-07 | 14 | Message Bus | 185 | 28.5054
2026-03-07 | 15 | Security | 185 | 28.5054
2026-03-07 | 8 | Test Plan | 185 | 28.5054
2026-03-08 | 10 | CM and setup | 190 | 29.2758
2026-03-08 | 6 | UX Design | 190 | 29.2758
2026-03-08 | 14 | Message Bus | 190 | 29.2758
2026-03-08 | 15 | Security | 190 | 29.2758
2026-03-08 | 8 | Test Plan | 190 | 29.2758
2026-03-09 | 10 | CM and setup | 195 | 30.0462
2026-03-09 | 6 | UX Design | 195 | 30.0462
2026-03-09 | 14 | Message Bus | 195 | 30.0462
2026-03-09 | 15 | Security | 195 | 30.0462
2026-03-09 | 8 | Test Plan | 195 | 30.0462
2026-03-10 | 10 | CM and setup | 200 | 30.8166
2026-03-10 | 6 | UX Design | 200 | 30.8166
2026-03-10 | 14 | Message Bus | 200 | 30.8166
2026-03-10 | 15 | Security | 200 | 30.8166
2026-03-10 | 8 | Test Plan | 200 | 30.8166
2026-03-11 | 6 | UX Design | 204 | 31.433
2026-03-11 | 14 | Message Bus | 204 | 31.433
2026-03-11 | 15 | Security | 204 | 31.433
2026-03-11 | 8 | Test Plan | 204 | 31.433
2026-03-12 | 15 | Security | 207 | 31.8952
2026-03-12 | 8 | Test Plan | 207 | 31.8952
2026-03-12 | 11 | UI Design | 207 | 31.8952
2026-03-13 | 15 | Security | 210 | 32.3575
2026-03-13 | 8 | Test Plan | 210 | 32.3575
2026-03-13 | 11 | UI Design | 210 | 32.3575
2026-03-14 | 15 | Security | 213 | 32.8197
2026-03-14 | 8 | Test Plan | 213 | 32.8197
2026-03-14 | 11 | UI Design | 213 | 32.8197
2026-03-15 | 15 | Security | 216 | 33.282
2026-03-15 | 8 | Test Plan | 216 | 33.282
2026-03-15 | 11 | UI Design | 216 | 33.282
2026-03-16 | 15 | Security | 219 | 33.7442
2026-03-16 | 8 | Test Plan | 219 | 33.7442
2026-03-16 | 11 | UI Design | 219 | 33.7442
2026-03-17 | 8 | Test Plan | 224 | 34.5146
2026-03-17 | 16 | Metrics DB | 224 | 34.5146
2026-03-17 | 21 | Regulations DB | 224 | 34.5146
2026-03-17 | 11 | UI Design | 224 | 34.5146
2026-03-17 | 20 | Workflows Repository | 224 | 34.5146
2026-03-18 | 8 | Test Plan | 229 | 35.2851
2026-03-18 | 16 | Metrics DB | 229 | 35.2851
2026-03-18 | 21 | Regulations DB | 229 | 35.2851
2026-03-18 | 11 | UI Design | 229 | 35.2851
2026-03-18 | 20 | Workflows Repository | 229 | 35.2851
2026-03-19 | 8 | Test Plan | 234 | 36.0555
2026-03-19 | 16 | Metrics DB | 234 | 36.0555
2026-03-19 | 21 | Regulations DB | 234 | 36.0555
2026-03-19 | 11 | UI Design | 234 | 36.0555
2026-03-19 | 20 | Workflows Repository | 234 | 36.0555
2026-03-20 | 8 | Test Plan | 239 | 36.8259
2026-03-20 | 16 | Metrics DB | 239 | 36.8259
2026-03-20 | 21 | Regulations DB | 239 | 36.8259
2026-03-20 | 11 | UI Design | 239 | 36.8259
2026-03-20 | 20 | Workflows Repository | 239 | 36.8259
2026-03-21 | 8 | Test Plan | 244 | 37.5963
2026-03-21 | 16 | Metrics DB | 244 | 37.5963
2026-03-21 | 21 | Regulations DB | 244 | 37.5963
2026-03-21 | 11 | UI Design | 244 | 37.5963
2026-03-21 | 20 | Workflows Repository | 244 | 37.5963
2026-03-22 | 17 | Members DB | 248 | 38.2126
2026-03-22 | 11 | UI Design | 248 | 38.2126
2026-03-22 | 20 | Workflows Repository | 248 | 38.2126
2026-03-22 | 9 | Test Harness | 248 | 38.2126
2026-03-23 | 17 | Members DB | 252 | 38.829
2026-03-23 | 11 | UI Design | 252 | 38.829
2026-03-23 | 20 | Workflows Repository | 252 | 38.829
2026-03-23 | 9 | Test Harness | 252 | 38.829
2026-03-24 | 17 | Members DB | 256 | 39.4453
2026-03-24 | 11 | UI Design | 256 | 39.4453
2026-03-24 | 20 | Workflows Repository | 256 | 39.4453
2026-03-24 | 9 | Test Harness | 256 | 39.4453
2026-03-25 | 17 | Members DB | 260 | 40.0616
2026-03-25 | 11 | UI Design | 260 | 40.0616
2026-03-25 | 20 | Workflows Repository | 260 | 40.0616
2026-03-25 | 9 | Test Harness | 260 | 40.0616
2026-03-26 | 17 | Members DB | 264 | 40.678
2026-03-26 | 11 | UI Design | 264 | 40.678
2026-03-26 | 20 | Workflows Repository | 264 | 40.678
2026-03-26 | 9 | Test Harness | 264 | 40.678
2026-03-27 | 11 | UI Design | 268 | 41.2943
2026-03-27 | 20 | Workflows Repository | 268 | 41.2943
2026-03-27 | 18 | Portfolios DB | 268 | 41.2943
2026-03-27 | 9 | Test Harness | 268 | 41.2943
2026-03-28 | 11 | UI Design | 272 | 41.9106
2026-03-28 | 20 | Workflows Repository | 272 | 41.9106
2026-03-28 | 18 | Portfolios DB | 272 | 41.9106
2026-03-28 | 9 | Test Harness | 272 | 41.9106
2026-03-29 | 11 | UI Design | 276 | 42.527
2026-03-29 | 20 | Workflows Repository | 276 | 42.527
2026-03-29 | 18 | Portfolios DB | 276 | 42.527
2026-03-29 | 9 | Test Harness | 276 | 42.527
2026-03-30 | 11 | UI Design | 280 | 43.1433
2026-03-30 | 20 | Workflows Repository | 280 | 43.1433
2026-03-30 | 18 | Portfolios DB | 280 | 43.1433
2026-03-30 | 9 | Test Harness | 280 | 43.1433
2026-03-31 | 11 | UI Design | 284 | 43.7596
2026-03-31 | 20 | Workflows Repository | 284 | 43.7596
2026-03-31 | 18 | Portfolios DB | 284 | 43.7596
2026-03-31 | 9 | Test Harness | 284 | 43.7596
2026-04-01 | 19 | Profiles DB | 287 | 44.2219
2026-04-01 | 9 | Test Harness | 287 | 44.2219
2026-04-01 | 12 | Manual | 287 | 44.2219
2026-04-02 | 19 | Profiles DB | 290 | 44.6841
2026-04-02 | 9 | Test Harness | 290 | 44.6841
2026-04-02 | 12 | Manual | 290 | 44.6841
2026-04-03 | 19 | Profiles DB | 293 | 45.1464
2026-04-03 | 9 | Test Harness | 293 | 45.1464
2026-04-03 | 12 | Manual | 293 | 45.1464
2026-04-04 | 19 | Profiles DB | 296 | 45.6086
2026-04-04 | 9 | Test Harness | 296 | 45.6086
2026-04-04 | 12 | Manual | 296 | 45.6086
2026-04-05 | 19 | Profiles DB | 299 | 46.0709
2026-04-05 | 9 | Test Harness | 299 | 46.0709
2026-04-05 | 12 | Manual | 299 | 46.0709
2026-04-06 | 9 | Test Harness | 305 | 46.9954
2026-04-06 | 23 | Metrics Access | 305 | 46.9954
2026-04-06 | 24 | Members Access | 305 | 46.9954
2026-04-06 | 25 | Portfolios Access | 305 | 46.9954
2026-04-06 | 12 | Manual | 305 | 46.9954
2026-04-06 | 27 | Workflows Access | 305 | 46.9954
2026-04-07 | 9 | Test Harness | 311 | 47.9199
2026-04-07 | 23 | Metrics Access | 311 | 47.9199
2026-04-07 | 24 | Members Access | 311 | 47.9199
2026-04-07 | 25 | Portfolios Access | 311 | 47.9199
2026-04-07 | 12 | Manual | 311 | 47.9199
2026-04-07 | 27 | Workflows Access | 311 | 47.9199
2026-04-08 | 9 | Test Harness | 317 | 48.8444
2026-04-08 | 23 | Metrics Access | 317 | 48.8444
2026-04-08 | 24 | Members Access | 317 | 48.8444
2026-04-08 | 25 | Portfolios Access | 317 | 48.8444
2026-04-08 | 12 | Manual | 317 | 48.8444
2026-04-08 | 27 | Workflows Access | 317 | 48.8444
2026-04-09 | 9 | Test Harness | 323 | 49.7689
2026-04-09 | 23 | Metrics Access | 323 | 49.7689
2026-04-09 | 24 | Members Access | 323 | 49.7689
2026-04-09 | 25 | Portfolios Access | 323 | 49.7689
2026-04-09 | 12 | Manual | 323 | 49.7689
2026-04-09 | 27 | Workflows Access | 323 | 49.7689
2026-04-10 | 9 | Test Harness | 329 | 50.6934
2026-04-10 | 23 | Metrics Access | 329 | 50.6934
2026-04-10 | 24 | Members Access | 329 | 50.6934
2026-04-10 | 25 | Portfolios Access | 329 | 50.6934
2026-04-10 | 12 | Manual | 329 | 50.6934
2026-04-10 | 27 | Workflows Access | 329 | 50.6934
2026-04-11 | 9 | Test Harness | 335 | 51.6179
2026-04-11 | 23 | Metrics Access | 335 | 51.6179
2026-04-11 | 24 | Members Access | 335 | 51.6179
2026-04-11 | 25 | Portfolios Access | 335 | 51.6179
2026-04-11 | 12 | Manual | 335 | 51.6179
2026-04-11 | 27 | Workflows Access | 335 | 51.6179
2026-04-12 | 9 | Test Harness | 341 | 52.5424
2026-04-12 | 23 | Metrics Access | 341 | 52.5424
2026-04-12 | 24 | Members Access | 341 | 52.5424
2026-04-12 | 25 | Portfolios Access | 341 | 52.5424
2026-04-12 | 12 | Manual | 341 | 52.5424
2026-04-12 | 27 | Workflows Access | 341 | 52.5424
2026-04-13 | 9 | Test Harness | 347 | 53.4669
2026-04-13 | 23 | Metrics Access | 347 | 53.4669
2026-04-13 | 24 | Members Access | 347 | 53.4669
2026-04-13 | 25 | Portfolios Access | 347 | 53.4669
2026-04-13 | 12 | Manual | 347 | 53.4669
2026-04-13 | 27 | Workflows Access | 347 | 53.4669
2026-04-14 | 9 | Test Harness | 353 | 54.3914
2026-04-14 | 23 | Metrics Access | 353 | 54.3914
2026-04-14 | 24 | Members Access | 353 | 54.3914
2026-04-14 | 25 | Portfolios Access | 353 | 54.3914
2026-04-14 | 12 | Manual | 353 | 54.3914
2026-04-14 | 27 | Workflows Access | 353 | 54.3914
2026-04-15 | 9 | Test Harness | 359 | 55.3159
2026-04-15 | 23 | Metrics Access | 359 | 55.3159
2026-04-15 | 24 | Members Access | 359 | 55.3159
2026-04-15 | 25 | Portfolios Access | 359 | 55.3159
2026-04-15 | 12 | Manual | 359 | 55.3159
2026-04-15 | 27 | Workflows Access | 359 | 55.3159
2026-04-16 | 12 | Manual | 364 | 56.0863
2026-04-16 | 27 | Workflows Access | 364 | 56.0863
2026-04-16 | 22 | Data Migration | 364 | 56.0863
2026-04-16 | 26 | Profiles Access | 364 | 56.0863
2026-04-16 | 28 | Regulations Access | 364 | 56.0863
2026-04-17 | 12 | Manual | 369 | 56.8567
2026-04-17 | 27 | Workflows Access | 369 | 56.8567
2026-04-17 | 22 | Data Migration | 369 | 56.8567
2026-04-17 | 26 | Profiles Access | 369 | 56.8567
2026-04-17 | 28 | Regulations Access | 369 | 56.8567
2026-04-18 | 12 | Manual | 374 | 57.6271
2026-04-18 | 27 | Workflows Access | 374 | 57.6271
2026-04-18 | 22 | Data Migration | 374 | 57.6271
2026-04-18 | 26 | Profiles Access | 374 | 57.6271
2026-04-18 | 28 | Regulations Access | 374 | 57.6271
2026-04-19 | 12 | Manual | 379 | 58.3975
2026-04-19 | 27 | Workflows Access | 379 | 58.3975
2026-04-19 | 22 | Data Migration | 379 | 58.3975
2026-04-19 | 26 | Profiles Access | 379 | 58.3975
2026-04-19 | 28 | Regulations Access | 379 | 58.3975
2026-04-20 | 12 | Manual | 384 | 59.168
2026-04-20 | 27 | Workflows Access | 384 | 59.168
2026-04-20 | 22 | Data Migration | 384 | 59.168
2026-04-20 | 26 | Profiles Access | 384 | 59.168
2026-04-20 | 28 | Regulations Access | 384 | 59.168
2026-04-21 | 27 | Workflows Access | 388 | 59.7843
2026-04-21 | 22 | Data Migration | 388 | 59.7843
2026-04-21 | 26 | Profiles Access | 388 | 59.7843
2026-04-21 | 28 | Regulations Access | 388 | 59.7843
2026-04-22 | 27 | Workflows Access | 392 | 60.4006
2026-04-22 | 22 | Data Migration | 392 | 60.4006
2026-04-22 | 26 | Profiles Access | 392 | 60.4006
2026-04-22 | 28 | Regulations Access | 392 | 60.4006
2026-04-23 | 27 | Workflows Access | 396 | 61.0169
2026-04-23 | 22 | Data Migration | 396 | 61.0169
2026-04-23 | 26 | Profiles Access | 396 | 61.0169
2026-04-23 | 28 | Regulations Access | 396 | 61.0169
2026-04-24 | 27 | Workflows Access | 400 | 61.6333
2026-04-24 | 22 | Data Migration | 400 | 61.6333
2026-04-24 | 26 | Profiles Access | 400 | 61.6333
2026-04-24 | 28 | Regulations Access | 400 | 61.6333
2026-04-25 | 27 | Workflows Access | 404 | 62.2496
2026-04-25 | 22 | Data Migration | 404 | 62.2496
2026-04-25 | 26 | Profiles Access | 404 | 62.2496
2026-04-25 | 28 | Regulations Access | 404 | 62.2496
2026-04-26 | 30 | Search Engine | 407 | 62.7119
2026-04-26 | 29 | Regulations Engine | 407 | 62.7119
2026-04-26 | 32 | Abstract Manager | 407 | 62.7119
2026-04-27 | 30 | Search Engine | 410 | 63.1741
2026-04-27 | 29 | Regulations Engine | 410 | 63.1741
2026-04-27 | 32 | Abstract Manager | 410 | 63.1741
2026-04-28 | 30 | Search Engine | 413 | 63.6364
2026-04-28 | 29 | Regulations Engine | 413 | 63.6364
2026-04-28 | 32 | Abstract Manager | 413 | 63.6364
2026-04-29 | 30 | Search Engine | 416 | 64.0986
2026-04-29 | 29 | Regulations Engine | 416 | 64.0986
2026-04-29 | 32 | Abstract Manager | 416 | 64.0986
2026-04-30 | 30 | Search Engine | 419 | 64.5609
2026-04-30 | 29 | Regulations Engine | 419 | 64.5609
2026-04-30 | 32 | Abstract Manager | 419 | 64.5609
2026-05-01 | 30 | Search Engine | 422 | 65.0231
2026-05-01 | 29 | Regulations Engine | 422 | 65.0231
2026-05-01 | 32 | Abstract Manager | 422 | 65.0231
2026-05-02 | 30 | Search Engine | 425 | 65.4854
2026-05-02 | 29 | Regulations Engine | 425 | 65.4854
2026-05-02 | 32 | Abstract Manager | 425 | 65.4854
2026-05-03 | 30 | Search Engine | 428 | 65.9476
2026-05-03 | 29 | Regulations Engine | 428 | 65.9476
2026-05-03 | 32 | Abstract Manager | 428 | 65.9476
2026-05-04 | 30 | Search Engine | 431 | 66.4099
2026-05-04 | 29 | Regulations Engine | 431 | 66.4099
2026-05-04 | 32 | Abstract Manager | 431 | 66.4099
2026-05-05 | 30 | Search Engine | 434 | 66.8721
2026-05-05 | 29 | Regulations Engine | 434 | 66.8721
2026-05-05 | 32 | Abstract Manager | 434 | 66.8721
2026-05-06 | 30 | Search Engine | 437 | 67.3344
2026-05-06 | 29 | Regulations Engine | 437 | 67.3344
2026-05-06 | 32 | Abstract Manager | 437 | 67.3344
2026-05-07 | 30 | Search Engine | 440 | 67.7966
2026-05-07 | 29 | Regulations Engine | 440 | 67.7966
2026-05-07 | 32 | Abstract Manager | 440 | 67.7966
2026-05-08 | 30 | Search Engine | 443 | 68.2589
2026-05-08 | 29 | Regulations Engine | 443 | 68.2589
2026-05-08 | 32 | Abstract Manager | 443 | 68.2589
2026-05-09 | 30 | Search Engine | 446 | 68.7211
2026-05-09 | 29 | Regulations Engine | 446 | 68.7211
2026-05-09 | 32 | Abstract Manager | 446 | 68.7211
2026-05-10 | 30 | Search Engine | 449 | 69.1834
2026-05-10 | 29 | Regulations Engine | 449 | 69.1834
2026-05-10 | 32 | Abstract Manager | 449 | 69.1834
2026-05-11 | 29 | Regulations Engine | 451 | 69.4915
2026-05-11 | 32 | Abstract Manager | 451 | 69.4915
2026-05-12 | 29 | Regulations Engine | 453 | 69.7997
2026-05-12 | 32 | Abstract Manager | 453 | 69.7997
2026-05-13 | 29 | Regulations Engine | 455 | 70.1079
2026-05-13 | 32 | Abstract Manager | 455 | 70.1079
2026-05-14 | 29 | Regulations Engine | 457 | 70.416
2026-05-14 | 32 | Abstract Manager | 457 | 70.416
2026-05-15 | 29 | Regulations Engine | 459 | 70.7242
2026-05-15 | 32 | Abstract Manager | 459 | 70.7242
2026-05-16 | 29 | Regulations Engine | 461 | 71.0324
2026-05-16 | 32 | Abstract Manager | 461 | 71.0324
2026-05-17 | 29 | Regulations Engine | 463 | 71.3405
2026-05-17 | 32 | Abstract Manager | 463 | 71.3405
2026-05-18 | 29 | Regulations Engine | 465 | 71.6487
2026-05-18 | 32 | Abstract Manager | 465 | 71.6487
2026-05-19 | 29 | Regulations Engine | 467 | 71.9569
2026-05-19 | 32 | Abstract Manager | 467 | 71.9569
2026-05-20 | 29 | Regulations Engine | 469 | 72.265
2026-05-20 | 32 | Abstract Manager | 469 | 72.265
2026-05-21 | 29 | Regulations Engine | 471 | 72.5732
2026-05-21 | 32 | Abstract Manager | 471 | 72.5732
2026-05-22 | 29 | Regulations Engine | 473 | 72.8814
2026-05-22 | 32 | Abstract Manager | 473 | 72.8814
2026-05-23 | 29 | Regulations Engine | 475 | 73.1895
2026-05-23 | 32 | Abstract Manager | 475 | 73.1895
2026-05-24 | 29 | Regulations Engine | 477 | 73.4977
2026-05-24 | 32 | Abstract Manager | 477 | 73.4977
2026-05-25 | 29 | Regulations Engine | 479 | 73.8059
2026-05-25 | 32 | Abstract Manager | 479 | 73.8059
2026-05-26 | 31 | Analysis Engine | 480 | 73.9599
2026-05-27 | 31 | Analysis Engine | 481 | 74.114
2026-05-28 | 31 | Analysis Engine | 482 | 74.2681
2026-05-29 | 31 | Analysis Engine | 483 | 74.4222
2026-05-30 | 31 | Analysis Engine | 484 | 74.5763
2026-05-31 | 31 | Analysis Engine | 485 | 74.7304
2026-06-01 | 31 | Analysis Engine | 486 | 74.8844
2026-06-02 | 31 | Analysis Engine | 487 | 75.0385
2026-06-03 | 31 | Analysis Engine | 488 | 75.1926
2026-06-04 | 31 | Analysis Engine | 489 | 75.3467
2026-06-05 | 31 | Analysis Engine | 490 | 75.5008
2026-06-06 | 31 | Analysis Engine | 491 | 75.6549
2026-06-07 | 31 | Analysis Engine | 492 | 75.8089
2026-06-08 | 31 | Analysis Engine | 493 | 75.963
2026-06-09 | 31 | Analysis Engine | 494 | 76.1171
2026-06-10 | 33 | Membership Manager | 497 | 76.5794
2026-06-10 | 34 | Market Manager | 497 | 76.5794
2026-06-10 | 35 | Performance Manager | 497 | 76.5794
2026-06-11 | 33 | Membership Manager | 500 | 77.0416
2026-06-11 | 34 | Market Manager | 500 | 77.0416
2026-06-11 | 35 | Performance Manager | 500 | 77.0416
2026-06-12 | 33 | Membership Manager | 503 | 77.5039
2026-06-12 | 34 | Market Manager | 503 | 77.5039
2026-06-12 | 35 | Performance Manager | 503 | 77.5039
2026-06-13 | 33 | Membership Manager | 506 | 77.9661
2026-06-13 | 34 | Market Manager | 506 | 77.9661
2026-06-13 | 35 | Performance Manager | 506 | 77.9661
2026-06-14 | 33 | Membership Manager | 509 | 78.4284
2026-06-14 | 34 | Market Manager | 509 | 78.4284
2026-06-14 | 35 | Performance Manager | 509 | 78.4284
2026-06-15 | 33 | Membership Manager | 512 | 78.8906
2026-06-15 | 34 | Market Manager | 512 | 78.8906
2026-06-15 | 35 | Performance Manager | 512 | 78.8906
2026-06-16 | 33 | Membership Manager | 515 | 79.3529
2026-06-16 | 34 | Market Manager | 515 | 79.3529
2026-06-16 | 35 | Performance Manager | 515 | 79.3529
2026-06-17 | 33 | Membership Manager | 518 | 79.8151
2026-06-17 | 34 | Market Manager | 518 | 79.8151
2026-06-17 | 35 | Performance Manager | 518 | 79.8151
2026-06-18 | 33 | Membership Manager | 521 | 80.2773
2026-06-18 | 34 | Market Manager | 521 | 80.2773
2026-06-18 | 35 | Performance Manager | 521 | 80.2773
2026-06-19 | 33 | Membership Manager | 524 | 80.7396
2026-06-19 | 34 | Market Manager | 524 | 80.7396
2026-06-19 | 35 | Performance Manager | 524 | 80.7396
2026-06-20 | 36 | Investor Portal | 527 | 81.2018
2026-06-20 | 37 | Investee Portal | 527 | 81.2018
2026-06-20 | 38 | Mobile App | 527 | 81.2018
2026-06-21 | 36 | Investor Portal | 530 | 81.6641
2026-06-21 | 37 | Investee Portal | 530 | 81.6641
2026-06-21 | 38 | Mobile App | 530 | 81.6641
2026-06-22 | 36 | Investor Portal | 533 | 82.1263
2026-06-22 | 37 | Investee Portal | 533 | 82.1263
2026-06-22 | 38 | Mobile App | 533 | 82.1263
2026-06-23 | 36 | Investor Portal | 536 | 82.5886
2026-06-23 | 37 | Investee Portal | 536 | 82.5886
2026-06-23 | 38 | Mobile App | 536 | 82.5886
2026-06-24 | 36 | Investor Portal | 539 | 83.0508
2026-06-24 | 37 | Investee Portal | 539 | 83.0508
2026-06-24 | 38 | Mobile App | 539 | 83.0508
2026-06-25 | 36 | Investor Portal | 542 | 83.5131
2026-06-25 | 37 | Investee Portal | 542 | 83.5131
2026-06-25 | 38 | Mobile App | 542 | 83.5131
2026-06-26 | 36 | Investor Portal | 545 | 83.9753
2026-06-26 | 37 | Investee Portal | 545 | 83.9753
2026-06-26 | 38 | Mobile App | 545 | 83.9753
2026-06-27 | 36 | Investor Portal | 548 | 84.4376
2026-06-27 | 37 | Investee Portal | 548 | 84.4376
2026-06-27 | 38 | Mobile App | 548 | 84.4376
2026-06-28 | 36 | Investor Portal | 551 | 84.8998
2026-06-28 | 37 | Investee Portal | 551 | 84.8998
2026-06-28 | 38 | Mobile App | 551 | 84.8998
2026-06-29 | 36 | Investor Portal | 554 | 85.3621
2026-06-29 | 37 | Investee Portal | 554 | 85.3621
2026-06-29 | 38 | Mobile App | 554 | 85.3621
2026-06-30 | 36 | Investor Portal | 557 | 85.8243
2026-06-30 | 37 | Investee Portal | 557 | 85.8243
2026-06-30 | 38 | Mobile App | 557 | 85.8243
2026-07-01 | 36 | Investor Portal | 560 | 86.2866
2026-07-01 | 37 | Investee Portal | 560 | 86.2866
2026-07-01 | 38 | Mobile App | 560 | 86.2866
2026-07-02 | 36 | Investor Portal | 563 | 86.7488
2026-07-02 | 37 | Investee Portal | 563 | 86.7488
2026-07-02 | 38 | Mobile App | 563 | 86.7488
2026-07-03 | 36 | Investor Portal | 566 | 87.2111
2026-07-03 | 37 | Investee Portal | 566 | 87.2111
2026-07-03 | 38 | Mobile App | 566 | 87.2111
2026-07-04 | 36 | Investor Portal | 569 | 87.6733
2026-07-04 | 37 | Investee Portal | 569 | 87.6733
2026-07-04 | 38 | Mobile App | 569 | 87.6733
2026-07-05 | 38 | Mobile App | 570 | 87.8274
2026-07-06 | 38 | Mobile App | 571 | 87.9815
2026-07-07 | 38 | Mobile App | 572 | 88.1356
2026-07-08 | 38 | Mobile App | 573 | 88.2897
2026-07-09 | 38 | Mobile App | 574 | 88.4438
2026-07-10 | 38 | Mobile App | 575 | 88.5978
2026-07-11 | 38 | Mobile App | 576 | 88.7519
2026-07-12 | 38 | Mobile App | 577 | 88.906
2026-07-13 | 38 | Mobile App | 578 | 89.0601
2026-07-14 | 38 | Mobile App | 579 | 89.2142
2026-07-15 | 39 | Manual Polishing | 582 | 89.6764
2026-07-15 | 40 | System Testing | 582 | 89.6764
2026-07-16 | 39 | Manual Polishing | 585 | 90.1387
2026-07-16 | 40 | System Testing | 585 | 90.1387
2026-07-17 | 39 | Manual Polishing | 588 | 90.6009
2026-07-17 | 40 | System Testing | 588 | 90.6009
2026-07-18 | 39 | Manual Polishing | 591 | 91.0632
2026-07-18 | 40 | System Testing | 591 | 91.0632
2026-07-19 | 39 | Manual Polishing | 594 | 91.5254
2026-07-19 | 40 | System Testing | 594 | 91.5254
2026-07-20 | 39 | Manual Polishing | 597 | 91.9877
2026-07-20 | 40 | System Testing | 597 | 91.9877
2026-07-21 | 39 | Manual Polishing | 600 | 92.4499
2026-07-21 | 40 | System Testing | 600 | 92.4499
2026-07-22 | 39 | Manual Polishing | 603 | 92.9122
2026-07-22 | 40 | System Testing | 603 | 92.9122
2026-07-23 | 39 | Manual Polishing | 606 | 93.3744
2026-07-23 | 40 | System Testing | 606 | 93.3744
2026-07-24 | 39 | Manual Polishing | 609 | 93.8367
2026-07-24 | 40 | System Testing | 609 | 93.8367
2026-07-25 | 41 | System Rollout | 613 | 94.453
2026-07-26 | 41 | System Rollout | 617 | 95.0693
2026-07-27 | 41 | System Rollout | 621 | 95.6857
2026-07-28 | 41 | System Rollout | 625 | 96.302
2026-07-29 | 41 | System Rollout | 629 | 96.9183
2026-07-30 | 41 | System Rollout | 633 | 97.5347
2026-07-31 | 41 | System Rollout | 637 | 98.151
2026-08-01 | 41 | System Rollout | 641 | 98.7673
2026-08-02 | 41 | System Rollout | 645 | 99.3837
2026-08-03 | 41 | System Rollout | 649 | 100

## Earned-Value Chart (Effort)
Time | ActivityId | ActivityName | Value | ValuePercentage
2026-01-05 | 0 |  | 0 | 0
2026-01-06 | 1 |  | 2.9 | 0.44684
2026-01-06 | 2 |  | 2.9 | 0.44684
2026-01-06 | 2 |  | 2.9 | 0.44684
2026-01-06 | 2 |  | 2.9 | 0.44684
2026-01-07 | 2 |  | 5.9 | 0.90909
2026-01-07 | 2 |  | 5.9 | 0.90909
2026-01-07 | 2 |  | 5.9 | 0.90909
2026-01-08 | 2 |  | 8.9 | 1.3713
2026-01-08 | 2 |  | 8.9 | 1.3713
2026-01-08 | 2 |  | 8.9 | 1.3713
2026-01-09 | 2 |  | 11.9 | 1.8336
2026-01-09 | 2 |  | 11.9 | 1.8336
2026-01-09 | 2 |  | 11.9 | 1.8336
2026-01-10 | 2 |  | 14.9 | 2.2958
2026-01-10 | 2 |  | 14.9 | 2.2958
2026-01-10 | 2 |  | 14.9 | 2.2958

## Earned-Value Chart (Progress)
Time | ActivityId | ActivityName | Value | ValuePercentage
2026-01-05 | 0 |  | 0 | 0
2026-01-06 | 2 | Requirements & Architecture | 2.5 | 0.38521
2026-01-07 | 2 | Requirements & Architecture | 5 | 0.77042
2026-01-08 | 2 | Requirements & Architecture | 7.5 | 1.1556
2026-01-09 | 2 | Requirements & Architecture | 10 | 1.5408
2026-01-10 | 2 | Requirements & Architecture | 12.5 | 1.926